## Initiation
Initiation Stage Business Case Calculations (see Planning Stage on next tab)
Benefits
Year | 1 | 2 | 3 | 4 | 5 | Total
1. Current Manufacturing Facility
Production (M) @ growth of 20% | 0.7 | 0.84 | 1.008 | 1.008 | 1.008 | 4.564 | <- At capacity after 36 months.
Cost (M) @ $60 / unit | 42 | 50.4 | 60.48 | 60.48 | 60.48 | 273.84
Marketing costs (M) @ $20 / unit | 14 | 16.8 | 20.16 | 20.16 | 20.16 | 91.28
Revenue @ $100 / unit | 70 | 84 | 100.8 | 100.8 | 100.8 | 456.4
Profit (M) | 14 | 16.8 | 20.16 | 20.16 | 20.16 | 91.28
2. New manufacturing facility
Production (M) @ growth of 40% | 1 | 1.4 | 1.96 | 2.744 | 3.8416 | 10.9456
Cost (M) @ $42 / unit | 42 | 58.8 | 82.32 | 115.248 | 161.3472 | 459.7152
Marketing costs (M) @ $20 / unit | 20 | 28 | 39.2 | 54.88 | 76.832 | 218.912
Revenue @ $100 / unit | 100 | 140 | 196 | 274.4 | 384.16 | 1094.56
Profit (M) | 38 | 53.2 | 74.48 | 104.272 | 145.9808 | 415.9328
3. Difference
Production (M) | 0.3 | 0.56 | 0.952 | 1.736 | 2.8336 | 6.3816
Cost (M) | 0 | 8.4 | 21.84 | 54.768 | 100.8672 | 185.8752
Marketing costs (M) | 6 | 11.2 | 19.04 | 34.72 | 56.672 | 127.632
Revenue | 30 | 56 | 95.2 | 173.6 | 283.36 | 638.16
Profit (M) | 24 | 36.4 | 54.32 | 84.112 | 125.8208 | 324.6528
Costs
1. Facility Procurement
Number of square meters of factory space | 5000
Cost per square meter of factory space | 1983.75
Total | 9918750
2. Building Material
All facility internal materials | 664999.995
Total | 664999.995
3. Hardware Procurement
Number of production lines | 3
Hardware cost per production line | 3325000.005
Management station | 106399.995
Control station | 199500
Magic dust | 664999.995
Total | 11344900.005
4. Software Procurement
Number of production lines | 3
Cost per production line | 1063999.995
Management station | 199500
Control station | 332500.005
Total | 4389000
5. Project Personnel
Project leads | 3990000
Project team | 10639999.995
Total | 14629999.995
6. Project Management
Project management team | 1861999.995
Risk budget | 4654999.995
Total | 6516999.99
Total Project Costs | 47464649.985
Benefit / Cost Ratio and Return On Investment
Year | 1 | 2 | 3 | 4 | 5
Cumulative additional profit (M) | 24 | 60.4 | 114.72 | 198.832 | 324.6528
Benefit / Cost Ratio (BCR) | 0.50564 | 1.2725 | 2.417 | 4.1891 | 6.8399
Return on investment (ROI) | -49.44% | 27.25% | 141.7% | 318.9% | 584%

## Planning
Planning Stage Business Case Calculations (see Initiation Stage on previous tab)
Benefits
Year | 1 | 2 | 3 | 4 | 5 | Total
1. Current Manufacturing Facility
Production (M) @ growth of 20% | 0.7 | 0.84 | 1.008 | 1.008 | 1.008 | 4.564 | <- At capacity after 36 months.
Cost (M) @ $60 / unit | 42 | 50.4 | 60.48 | 60.48 | 60.48 | 273.84
Marketing costs (M) @ $20 / unit | 14 | 16.8 | 20.16 | 20.16 | 20.16 | 91.28
Revenue @ $100 / unit | 70 | 84 | 100.8 | 100.8 | 100.8 | 456.4
Profit (M) | 14 | 16.8 | 20.16 | 20.16 | 20.16 | 91.28
2. New manufacturing facility
Production (M) @ growth of 40% | 1 | 1.4 | 1.96 | 2.744 | 3.8416 | 10.9456
Cost (M) @ $42 / unit | 42 | 58.8 | 82.32 | 115.248 | 161.3472 | 459.7152
Marketing costs (M) @ $20 / unit | 20 | 28 | 39.2 | 54.88 | 76.832 | 218.912
Revenue @ $100 / unit | 100 | 140 | 196 | 274.4 | 384.16 | 1094.56
Profit (M) | 38 | 53.2 | 74.48 | 104.272 | 145.9808 | 415.9328
3. Difference
Production (M) | 0.3 | 0.56 | 0.952 | 1.736 | 2.8336 | 6.3816
Cost (M) | 0 | 8.4 | 21.84 | 54.768 | 100.8672 | 185.8752
Marketing costs (M) | 6 | 11.2 | 19.04 | 34.72 | 56.672 | 127.632
Revenue | 30 | 56 | 95.2 | 173.6 | 283.36 | 638.16
Profit (M) | 24 | 36.4 | 54.32 | 84.112 | 125.8208 | 324.6528
Costs
1. Facility Procurement
Number of square meters of factory space | 5000
Cost per square meter of factory space | 1850
Total | 9250000
2. Building Material
All facility internal materials | 565000
Total | 565000
3. Hardware Procurement
Number of production lines | 3
Hardware cost per production line | 3000000
Management station | 100000
Control station | 200000
Magic dust | 777000
Total | 10477000
4. Software Procurement
Number of production lines | 3
Cost per production line | 1100000
Management station | 200000
Control station | 300000
Total | 4400000
5. Project Personnel
Project leads | 3283000
Project team | 9680000
Security consultant | 66400 | <-- New from Initiation stage.
Total | 13029400
6. Project Management
Project management team | 1695960
Risk budget | 5050000
Total | 6745960
Total Project Costs | 44467360
Benefit / Cost Ratio and Return On Investment
Year | 1 | 2 | 3 | 4 | 5
Cumulative additional profit (M) | 24 | 60.4 | 114.72 | 198.832 | 324.6528
Benefit / Cost Ratio (BCR) | 0.53972 | 1.3583 | 2.5799 | 4.4714 | 7.3009
Return on investment (ROI) | -46.03% | 35.83% | 158% | 347.1% | 630.1%