Project Charter

for the

Magical Devices Version 3 (MDV3)
Project

20YY-MM-DD

Prepared by:

Charles Wallace, Project Manager

Approved by:

Lucy Pevensie, President Magical Devices, Project Sponsor

This document provides a realistic example of a professional Project Charter for a

significantly sized $44M project with multiple domains.  Feel free to share this

document and the MDV3 project with anyone you wish.  Let’s help everyone.

The Project Charter should not be too detailed or stray into planning activities themselves.  Only the subsequent planning stage can produce a Project Management Plan with a reliable schedule and budget estimate accurate within +/- 10%, and provide the information the Sponsor needs to decide whether or not to authorize proceeding to the execution stage.  The Project Charter should provide just enough information for the Sponsor to be able to decide whether or not to authorize moving forward to the Planning stage, and for the Project Manager to then conduct efficient and productive planning.

One of the most important principles of project management is that project execution should only be authorized after a complete and accurate Project Management Plan has been prepared, which then provides the level of detail on scope, schedule, budget, and risks the Sponsor needs to safely authorize the execution stage.  See the subsequent document

“MDV3 Project Management Plan” for more information.

Contents

1.	Executive Summary	1

2.	Sponsor	2

3.	Customer	2

4.	Scope	3

4.1	Objective	3

4.2	Assumptions	3

4.3	Constraints	3

5.	Conceptual Solution	4

6.	Business Case	5

6.1	Options	5

6.2	Assumptions	5

6.3	Benefits	6

6.4	Costs	6

6.5	Analysis	7

7.	Stakeholders	8

8.	Risks	10

9.	Project Manager	10

List of Figures

Figure 1 - Conceptual Solution	4

List of Tables

Table 1 - Project Benefits	6

Table 2 - Project Costs	7

Table 3 - Project BCR and ROI	7

Executive Summary

This charter provides the Initiation stage description of the Magical Devices Version 3 (MDV3) project, a major upgrade of the company manufacturing capability to help ensure Magical Devices continued success.  This charter also authorizes the Project Manager to prepare a complete and accurate project plan for presentation to the Sponsor for final decision making and potential approval for proceeding to the Execution stage.

This project supports the following objective from the Magical Devices Strategic Plan: “Magical Devices shall ensure we have sufficient manufacturing capacity to produce the most advanced magical devices with the highest quality at the lowest cost to meet projected market demand for the next ten years”.

The project has been initiated to respond to the following need.  Magical Devices version 2 have been selling well for the past several years with excellent results.  However, recent innovations in the field of magic, together with the results from our research and development projects, indicate it is possible to increase the effectiveness of the devices by at least 60%.  At the same time, advances in magic manufacturing equipment and processes indicate that next generation devices could be produced at a cost at least 30% lower than with our current facility.

In addition, user demand for the version 2 devices has been growing at a rate of 20% a year.  Projections show that, even with the retrofits currently planned, the existing manufacturing facility will reach production capacity within 36 months.

Therefore, Magical Devices have identified a potential opportunity to build a new manufacturing facility capable of producing a more effective suite of magical devices that will generate even greater market demand, produced at a lower cost, and with capacity that combined with our existing facility will be able to meet anticipated demand for at least the next decade.

Sponsor

Lucy Pevensie, President of Magical Devices, is the sponsor of this project, responsible for the project funding, and the authority for approval of the project plan and any changes to the baseline if approved for execution.

Customer

Three customer groups have been identified representing the end-users of the project, responsible for participation in definition of the project scope, and responsible for sign-off of the requirements and acceptance of the final deliverables if the project is approved for proceeding to execution:

- Ava Lee, VP of Customer Satisfaction.  Represents the consumer end-users of the magic devices, and is responsible for ensuring the functional requirements for version 3 of the magical devices are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the final device configuration.

- Ezekiel Rawlins, Magical Devices VP Manufacturing.  Represents the production end-users of the project, and is responsible for ensuring the requirements for the production lines are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the final equipment and production line configuration.

- Dave Robicheaux, Magical Devices Director of Facilities & Operations.  Represents the facility and operations end-users of the project, and is responsible for ensuring the requirements for the facility are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the facility configuration and support programs.

Scope

This section describes the project objective and current assumptions and constraints.

Objective

The project objective is:

- Develop a manufacturing facility capable of producing a version 3 release of Magical Devices with 60% greater effectiveness, at 30% less cost, able to meet demand growing by 40% a year for the next five years, by the end of fiscal year 20YY.

Assumptions

The project assumptions are:

- The site acquired last year adjacent to our current facility has sufficient space, power, water, and other resources required for development of the new facility.

- Office staff shall remain in the current facility, and the two facilities shall be connected by an enclosed walkway.

- This project does not need to consider staffing requirements since the Magical Devices human resources department will provide all required personnel as part of their existing growth plans.

Constraints

The project constraints are:

- The budget for this project must not exceed the planned budget of $47,464,650.

- The total schedule for the project must not exceed 36 months.

- Pilot operation of the first production line must begin within 25 months from project start.

- The manufacturing system must fully comply with all requirements of the Magical Management Institute (MMI) industry standard Secure Magical Device Manufacturing (MMI-321123-G).

Conceptual Solution

The conceptual solution to be developed to meet the project objective is a new manufacturing facility that uses the most modern and efficient production methods, new business processes, the most recent equipment hardware, and enhanced software capable of producing version 3 magical devices implementing the features made possible by the innovations developed by our research and development lab.

A top-level diagram of the conceptual solution is provided below.

Figure 1 - Conceptual Solution

Business Case

This section describes the initiation stage business case.  In summary, the analysis indicates the ROI turns positive in year 2, and is more than 500% in year 5.  This suggests the project will likely provide much more benefit than it costs, and so the effort has been prioritized for planning by the Magical Devices Board of Directors.

Since this initiation estimate was based on hard information available from the previous Version 2 facility build, the team believes the estimate is unusually accurate, likely within +/- 30%.  However, the estimate will be revisited at the end of planning when much improved planning level detail is available, at which point the planned cost and schedule should have a likely accuracy of +/- 10%, which will then be sufficient for the sponsor to make final decisions.

The spreadsheet for the initiation stage business case calculations can be found in the file “MDV3 Business Case Calculations”.  More information on the options considered, assumptions, constraints, costs, benefits, and analysis can be found in the following sections.

Options

Three options were examined during preparation of the business case:

- Upgrade the current manufacturing facility.  This option was not chosen because the costs were estimated to be prohibitive, it would interrupt current production, and it would not be possible to build the capacity for expected growth in the market in the current space.

- Outsource production to third party providers.  This option was not selected because there is currently no critical mass of suppliers producing magical devices enabling competitive outsourcing, and would make the rapid innovation of enhancements required to stay competitive in the new and rapidly changing magical devices segment more difficult.

- Build a new manufacturing facility.  This option was selected since it would not interrupt current production, it would allow the most rapid in-house innovation to respond to market input as version 4 and later devices are developed, and it provided the greatest five year economic benefit.

Assumptions

The business case is based on the following assumptions:

- The feasibility study and pilot projects conducted by the Research and Development department indicates it is possible to build version 3 magical devices with an at least 60% increase in effectiveness over version 2.

- The marketing study and analysis conducted by the Business Development department indicates that version 3 magical devices with 60% greater effectiveness will generate a doubling of current year over year growth in market demand to 40%.

- The research and pilot projects conducted by the manufacturing department indicate updated processes and equipment can reduce the production cost (manufacturing and operating) per device by at least 30%.

- Marketing costs of $20 per unit and revenue of $100 per unit will not change.

- The costs for developing the new facility will be 15% greater per square meter than experienced for the build of the version 2 facility.  A new facility of size 5,000 square meters will be needed to meet the anticipated growth in demand over the next five years.

- The costs for the hardware, software, project personnel, and project management costs will be 50% greater than experienced for build of the version 2 facility.

- This project does not need to consider decommissioning and sell-off of the version 2 equipment.  It is assumed the current facility will be kept in operation for manufacture of version 2 devices for the secondary market for at least two years following open of the version 3 facility, following which a separate project will address retrofit of the version 2 facility to meet the additional demand for version 3 devices in years six through ten.

Benefits

The benefits of the project are defined by the additional to be profit obtained from the new facility, calculated as the difference between the profits from the version 3 facility and the profits from continued use of the version 2 facility.

The following table estimates the production level, production costs, marketing costs, revenue, and profit for the current manufacturing facility, the new manufacturing facility, and the difference over five years.  The current facility reaches maximum production capacity in year 3.

| Year | 1 | 2 | 3 | 4 | 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Current Manufacturing Facility |  |  |  |  |  |  |
| Production (M) @ growth of 20% | 0.7 | 0.84 | 1.01 | 1.01 | 1.01 | 4.56 |
| Cost (M) @ $60 / unit | $42 | $50 | $60 | $60 | $60 | $274 |
| Marketing costs (M) @ $20 / unit | $14 | $17 | $20 | $20 | $20 | $91 |
| Revenue @ $100 / unit | $70 | $84 | $101 | $101 | $101 | $456 |
| Profit (M) | $14 | $17 | $20 | $20 | $20 | $91 |
| 2. New manufacturing facility |  |  |  |  |  |  |
| Production (M) @ growth of 40% | 1. | 1.4 | 1.96 | 2.74 | 3.84 | 10.95 |
| Cost (M) @ $42 / unit | $42 | $59 | $82 | $115 | $161 | $460 |
| Marketing costs (M) @ $20 / unit | $20 | $28 | $39 | $55 | $77 | $219 |
| Revenue @ $100 / unit | $100 | $140 | $196 | $274 | $384 | $1,095 |
| Profit (M) | $38 | $53 | $74 | $104 | $146 | $416 |
| 3. Difference |  |  |  |  |  |  |
| Production (M) | 0.3 | 0.56 | 0.95 | 1.74 | 2.83 | 6.38 |
| Cost (M) | $0 | $8 | $22 | $55 | $101 | $186 |
| Marketing costs (M) | $6 | $11 | $19 | $35 | $57 | $128 |
| Revenue | $30 | $56 | $95 | $174 | $283 | $638 |
| Profit (M) | $24 | $36 | $54 | $84 | $126 | $325 |

Table 1 - Project Benefits

Costs

The estimated costs for the project are based on the business case assumptions of a 15% increase in the cost per square meter for the new facility build, and costs for the building material, hardware, software, project personnel, and project management 50% greater than for build of the version 2 facility.  The following table provides a summary of the cost estimates.

| 1. Facility Procurement |  |
| --- | --- |
| Number of square meters of factory space | 5000 |
| Cost per square meter of factory space | $1,984 |
| Total | $9,918,750 |
| 2. Building Material |  |
| All facility internal materials | $665,000 |
| Total | $665,000 |
| 3. Hardware Procurement |  |
| Number of production lines | 3 |
| Hardware cost per production line | $3,325,000 |
| Management station | $106,400 |
| Control station | $199,500 |
| Magic dust | $665,000 |
| Total | $11,344,900 |
| 4. Software Procurement |  |
| Number of production lines | 3 |
| Cost per production line | $1,064,000 |
| Management station | $199,500 |
| Control station | $332,500 |
| Total | $4,389,000 |
| 5. Project Personnel |  |
| Project leads | $3,990,000 |
| Project team | $10,640,000 |
| Total | $14,630,000 |
| 6. Project Management |  |
| Project management team | $1,862,000 |
| Risk budget | $4,655,000 |
| Total | $6,517,000 |
| Total Project Costs | $47,464,650 |

Table 2 - Project Costs

Analysis

The expected additional profit was compared to the project costs, and the benefit / cost ratio (BCR) and return on investment (ROI) calculated over five years, as shown in the table below.

| Year | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Cumulative additional profit (M) | $24 | $60 | $115 | $199 | $325 |
| Benefit / Cost Ratio (BCR) | 0.51 | 1.27 | 2.42 | 4.19 | 6.84 |
| Return on investment (ROI) | -49% | 27% | 142% | 319% | 584% |

Table 3 - Project BCR and ROI

The analysis indicates the ROI turns positive in year 2, and is more than 500% in year 5.  This analysis shows the project will likely provide much more benefit than it costs, and so it has been prioritized for planning by the Magical Devices Board of Directors.  Final decisions about proceeding to execution will be made once the project management plan has been prepared.

Stakeholders

This section describes the MDV3 key stakeholders.  The project stakeholders are affected and can affect the project, and therefore will be included in definition of the project scope and development of the project plan, and will be included in regular communications as the project progresses if approved for execution.

The key project stakeholders, along with their role, key need, priorities, and planned communications are described in the Stakeholder Register provided below.  This register can also be found in the attached document “MDV3 Stakeholder Register”.

| Name | Role | Key Need | Priorities | Communications |
| --- | --- | --- | --- | --- |
| Lucy Pevensie | Magical Devices President | Additional revenue generation. | Schedule, Cost, Scope | • Monthly project review update. |
| Ava Lee | Magical Devices VP Customer Satisfaction | Enhanced version 3 magical devices with at least 80 greater effectiveness. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for device design and development, coordination of device user reviews. |
| Solomon Gursky | Magical Devices VP Finance | Cost control. | Cost, Schedule, Scope | • Monthly project review update. • Immediate notification of any unexpected cost changes. |
| Ezekiel Rawlins | Magical Devices VP Manufacturing | The latest manufacturing processes and equipment. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for production line build and test, inspections, and user reviews. |
| Stephanie Plum | Magical Devices VP Human Resources | Timely notification of any changes in plans for staffing growth. | Schedule, Scope, Cost | • Monthly project review update. • Immediate notification of any changes in schedule. |
| Jack Reacher | Magical Devices VP Marketing & Sales | Knowledge of new device features and schedule availability. | Schedule, Scope, Cost | • Monthly project review update. • Immediate notification of any changes to scope. |
| Dave Robicheaux | Magical Devices Director of Facilities & Operations | Standards compliant and supportable facility. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for facility build and test, inspections, and user reviews. |
| Travis McGee | Mayor Oakville | Advance notice of hiring plans and schedule. | Schedule | • Monthly updates by phone or meeting from the President. • Immediate notification of any changes in hiring plans. • Invitation to facility opening. |
| Meg Murray | Executive Director Magical Management Institute (MMI) | Assurance of compliance with Magical Management Institute Regulations. | Scope | • Quarterly updates on project progress and regulatory compliance. • Invitation to facility opening. |

Risks

Significant risks identified at the initiation stage to be further considered during planning are described below:

- Integration of a complex and innovative set of equipment caused unexpected incompatibilities requiring additional unplanned integration work in the build of the Magical Devices Version 2 facility, and so may be expected to occur for the Version 3 build.

- Manufacturing system compliance with the requirements of the industry standard Secure Device Manufacturing & Operations (MMI-321123-G) from the Magical Management Institute is required for certification of the Magical Devices Version 3 as MMI approved, and so effectively constitutes a showstopper to production.  The requirements of this standard are very specific and demanding.  If the production system does not pass the associated Security Certification test at the end of system build, the certification will be delayed until deficiencies are corrected, preventing opening of the facility, startup of production, and delaying availability of the devices on the market.

- Despite building on near feature complete prototypes developed by the Magical Devices software research and development group, the software development required for development of fully production level version 3 magical devices that incorporate a highly sophisticated feature set may be expected to make accurate estimation of the work challenging, based on the experience with the significant software schedule extension experienced with development of the version 2 devices.

Project Manager

The assigned Project Manager shall prepare an optimized plan documenting the MDV3 project scope, schedule, budget, and risks for sponsor review before proceeding to the Execution stage.

The Project Manager is authorized to call on support from within and outside the organization as required to prepare a complete and accurate plan.

The Project Manager, planning budget, and planning schedule are defined as follows:

- Project Manager:  Charles Wallace, charles.wallace@@@@@.com, 123-456-7890

- Planning Budget:  5% of the estimated project cost of $47,464,650, or $2,373,232.

- Planning Schedule:   Project Plan ready for review on 20BB-MM-DD.