## MDV3 Requirements
ID | Type | Requirement | Owner | Deliverable | Test Case | Test Status
1000 | Functionality | The magical devices shall be compliant with all requirements in the industry standard "Magic Componentry Functionality Standard" (Version 10.52) from the Magical Management Institute. | Ava Lee | SYB1.3 | SYTP1.4 | TBD
1100 | Functionality | The magical devices shall weigh less than 10 grams. | Ava Lee | HWD1.3 | QAHW1.3 | TBD
1200 | Functionality | The magical devices shall be capable of suspension of time for at least ten hours in the local universal neighborhood. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1300 | Functionality | The magical devices shall be capable of teleportation over a distance of at least 100 meters. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1400 | Functionality | The magical devices shall be capable of projection of holographic sightscapes that are dynamic and indistinguishable from reality from any angle and in any lighting. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1500 | Functionality | The magical devices shall be automatically updatable over the Internet and by telekinesis. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1600 | Functionality | The magical devices shall be remotely callable and able to transport themselves to the users location from anywhere on the planet. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1700 | Functionality | The magical devices shall be configurable to disguise themselves as a normal looking computer, book, or kitten. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1800 | Functionality | The magical devices shall be able to cooperate with other devices in the same network over WIFI and telecommunications networks. | Ava Lee | SWD1.3 | QASW1.5 | TBD
1900 | Functionality | The magical devices shall be capable of transmutation of any metal or noble gas. | Ava Lee | SWD1.3 | QASW1.5 | TBD
2000 | Functionality | The magical devices shall be producible in any colour, including iridescent. | Ava Lee | SWD1.3 | QASW1.5 | TBD
2100 | Facility | The manufacturing facility shall be compliant with all requirements of the Magical Management Institute standard "Magic Manufacturing Requirements And Specifications" (MMI-654321-D). | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
2200 | Facility | The facility shall fully comply with all requirements of the Magical Management Institute standard "Safe Production Of Devices With Magical Properties" (MMI-987654-E). | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
2300 | Facility | The facility shall include separate material staging and shipping lines for rapidly decongested material management. | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
2400 | Facility | The facility shall comply with all requirements of the standard Design Considerations for "Airborne Molecular Contamination Filtration Systems" (IEST-G-CC035.1). | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
2500 | Equipment | The production lines shall include equipment to provide staging, piece build, assembly, finishing, and QA functions. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
2600 | Equipment | The production equipment shall comply with all requirements of the standard "Vibration Monitoring" (ISO 10816). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
2700 | Equipment | The production equipment shall comply with all requirements of the standard "Acoustic Emissions" (ISO 22096). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
2800 | Equipment | The production equipment shall comply with all requirements of "Nanotechnologies Materials Specifications" (ISO 12805). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
2900 | Equipment | All production equipment shall run on 220V grounded power. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
3000 | Equipment | All production equipment shall incorporate single function emergency shutdown features. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
3100 | Equipment | All production equipment shall use industry standard interfaces capable of connecting to equipment from any other vendor using the same standard interface. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 | TBD
3200 | Management Station | The facility shall include a management station capable of instrumentation reporting and control over all production lines. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
3300 | Management Station | The management station software shall provide longitudinal tracking of all production line performance over time, with reporting available on quantity, productivity, efficiency, and availability, and be available broken down by mode, phase, and device type. | Ezekiel Rawlins | SWD1.3 | QASW1.5 | TBD
3400 | Management Station | The management station software shall provide single screen dynamic dashboards tracking the performance of each production line. | Ezekiel Rawlins | SWD1.3 | QASW1.5 | TBD
3500 | Control Station | The facility shall include independent control stations for each of the three production lines each providing separate integration, control, and reporting functionality. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
3600 | Control Station | The control station software shall be able to control all equipment on a production line from the allocated production station. | Ezekiel Rawlins | SWD1.3 | QASW1.5 | TBD
3700 | Control Station | The control station software for any production line shall be configurable to be able to simultaneously control any of the other production lines. | Ezekiel Rawlins | SWD1.3 | QASW1.5 | TBD
3800 | Supportability | The computing and manufacturing equipment componentry shall all be off-the-shelf and available from multiple suppliers. | Dave Robicheaux | HWD1.3 | QAHW1.3 | TBD
3900 | Supportability | All equipment vendors shall utilize a quality assurance system that complies with all requirements of "Quality Management System" (CLSI QMS13-A). | Dave Robicheaux | HWD1.3 | QAHW1.3 | TBD
4000 | Supportability | All operating system and middleware shall be free open source software. | Dave Robicheaux | SWD1.3 | QASW1.5 | TBD
4100 | Regulatory | The manufacturing system shall be compliant with all security requirements in the industry standard "Secure Magical Device Manufacturing" (MMI-321123-G) from the Magical Management Institute. | Ava Lee | FACD1.4 | QASE1.1 | TBD
4200 | Regulatory | The devices shall be compliant with all requirements in the industry standard "Magic Componentry Functionality Standard (V10.52)" from the Magical Management Institute. | Ava Lee | SYB1.3 | SYTP1.4 | TBD
4300 | Capacity | The facility shall be capable of producing 1M units in year 1 of operation. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
4400 | Capacity | The facility shall be capable of production growth of 40% a year for at least ten years. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
4500 | Capacity | The facility shall be capable of producing version 1 and version 2 magical devices and component parts to provide long-term customer support. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
4600 | Capacity | The facility's three production lines shall each be configurable to be able to produce health, education, and environment devices. | Ezekiel Rawlins | FACD1.4 | FACI1.7 | TBD
4700 | Availability | A failure in any single component shall not bring down the production capacity by more than 10%. | Dave Robicheaux | HWD1.3 | QASY1.2 | TBD
4800 | Availability | The manufacturing system shall have 99.999% uptime. | Ezekiel Rawlins | SYB1.3 | SYTP1.4 | TBD
4900 | Availability | The production equipment shall be capable of 24/7/365 operation. | Dave Robicheaux | SYB1.3 | SYTP1.4 | TBD
5000 | Availability | The production equipment shall be capable of component level swap and replace for repair of any faults. | Dave Robicheaux | HWD1.3 | QAHW1.3 | TBD
5100 | Environmental | The facility shall create zero untreated waste. | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
5200 | Environmental | The facility shall use renewable energy for all power requirements. | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
5300 | Environmental | All packaging shall be fully recyclable. | Dave Robicheaux | SYB1.3 | SYTP1.4 | TBD
5400 | Environmental | The facility shall comply with all requirements of "Environmental Management Systems" (ISO 14001). | Dave Robicheaux | FACD1.4 | FACI1.7 | TBD
5500 | Security | The facility shall be secure from unauthorized access, with secure biometric authentication required for entry. | Dave Robicheaux | FACD1.4 | QASE1.1 | TBD
5600 | Security | Logon for operation and control of all equipment and control and management stations shall be by secure biometric access. | Ezekiel Rawlins | SWD1.3 | QASW1.5 | TBD
5700 | Training | The training solution shall provide hands-on skills training immediately before deployment of each phase. | Ezekiel Rawlins | TRM1.4 | TRM1.4 | TBD
5800 | Training | The training solution shall include online self serve refreshment training resources. | Ezekiel Rawlins | TRM1.4 | TRM1.4 | TBD
5900 | Marketing | The magical devices shall be orderable online and fully customizable to the customer's requirements. | Jack Reacher | SYB1.3 | SYTP1.4 | TBD
6000 | Marketing | A device ordered online shall immediately enter the manufacturing queue, and be automatically shipped to the customer address when ready. | Jack Reacher | SWD1.3 | QASW1.5 | TBD
6100 | Procurement | All equipment vendors shall be ISO 9001 certified. | Ezekiel Rawlins | FACB1.1 | FACB1.1 | TBD
6200 | Procurement | The facility building contractor shall have experience building at least five manufacturing facilities of 5,000 square meters or larger within the last five years. | Dave Robicheaux | FACB1.1 | FACB1.1 | TBD