## Slide 1
Magical Devices V3 (MDV3)
Business Process
System
Hardware
Business Processes As-Is Draft
Business Processes As-Is Final
Business Processes To-Be Draft
Business Processes To-Be Final
System Architecture
System Build
System Certification
Hardware Design
Hardware Build
Hardware Test Planning
Security
Security Design
Security Test
Software
Software Planning
Software Design
Software Test Planning
Software Build
Software Test
Security Test Planning
Gap Analysis Draft
Gap Analysis Final
System Architecture Draft
System Architecture Final
System Build 1
System Build 2
System Build 2 Test
System Build Final
System Certification Final
System Test
System Build 1 Test
Hardware Planning
Hardware Development Plan
Hardware Detailed Requirements
Hardware Design Draft 1
Hardware Design Draft 2
Hardware Design Final
Hardware Procurement
Hardware Build 1
Hardware Build 2
Hardware Build 3
Hardware Build Final
Hardware Test Plan
Hardware Test Procedures Draft 1
Hardware Test Procedures Draft 2
Hardware Test
Hardware Test Procedures Final
Hardware Build 1 Test
Hardware Build 2 Test
Hardware Build 3 Test
System Test Planning
System Test Plan
System Test Procedures Draft 1
System Test Procedures Draft 2
System Test Procedures Final
Facility
Training
Support
Software Detailed Requirements
Software Development Plan
Software Design Draft 1
Software Design Draft 2
Software Design Final
Software Test Plan
Software Test Procedures Draft 1
Software Test Procedures Draft 2
Software Test Procedures Final
Software Procurement
Software Sprint 1
Software Sprint 2
Software Sprint 3
Software Sprint 4
Software Final
Software Sprint 1 Test
Software Sprint 2 Test
Software Sprint 3 Test
Software Sprint 4 Test
Security Detailed Requirements
Security Architecture
Security Test Plan
Security Test Procedures Draft
Security Test Procedures Final
Security Certification
Security Test
Security Certification Final
Implementation
Implementation Planning
Implementation Phase 1
Implementation Phase 2
Implementation Phase 3
Implementation Plan Draft 1
Implementation Plan Draft 2
Implementation Plan Draft 3
Implementation Plan Draft 4
Implementation Plan Final
Phase 2 Training
Phase 1 Pilot
Phase 1 Support Transition
Phase 1 Training
Phase 2 Pilot
Phase 2 Support Transition
Phase 3 Pilot
Phase 3 Rollout
Phase 3 Training
Training Material
Training Phases
Phase Support
Support Package
Phase 1 Rollout
Phase 2 Rollout
Training Material Draft 1
Training Material Draft 2
Training Material Draft 3
Training Material Final
Support Package Draft 1
Support Package Draft 2
Support Package Draft 3
Support Package Final
Facilities Planning
Facilities Design
Facilities Build
Facilities Detailed Requirements
Facilities Build Plan
Facilities Design Draft 1
Facilities Design Draft 2
Facilities Design Draft 3
Facilities Design Final
Facilities Build 1
Facilities Build 2
Facilities Build 3
Facilities Build 4
Facilities Build Final
Business Process As-IS
Business Process To-Be
Gap Analysis
Project Management
Project Management Activities
Project Closure
Project Management Office
Kick-off Meeting
Project Closure Readiness Review
Final Procurements Closure
Lessons Learned Report
Project Final Report
Implementation Readiness Review
Phase 3 Support Transition
Facilities Procurement
Training Planning
Training Detailed Requirements
Training Plan
Support Planning
Support Detailed Requirements
Support Plan
Facilities
Build 5
Facilities Inspection
Facilities Inspection Build 1
Facilities Inspection Build 2
Facilities Inspection Build 3
Facilities Inspection Build 4
Facilities Inspection Build 5
Facilities Inspection Build 6
Facilities Inspection Build 7
Facilities
Build 7
Facilities
Build 6
Quality Assurance
Software Sprint 5
Software Sprint 5 Test
Risk Budget
Risk Buffer
Magical Devices Version 3 (MDV3)
Work Breakdown Structure (WBS)
Magical Devices V3 (MDV3)
Business Process
Software
Support
Security
Implementation
Facility
Project Management
Training
System
Hardware
Quality Assurance
Magical Devices Version 3 (MDV3)
Work Breakdown Structure (WBS)
Summary Level