## WBS Dictionary
WBS ID | Work Breakdown Structure Deliverable | Description | Owner | Cost Account
MDV3 | Magical Devices Version 3 | The entire MDV3 project. | Charles Wallace | CA1000
BPR1 | Business Process | Develop baselines for the as-is business processes, the to-be business processes, and then perform a gap analysis to determine what work is needed to implement the to-be processes. | Kong Qiu | CA2000
BPRA1 | Business Process As-Is | Collect and document the existing set of as-is business processes to provide a consolidated baseline. | Kong Qiu | CA3000
BPRA1.1 | Business Processes As-Is Draft | Gather a consolidated, organized baseline of all the current business processes used to produce version 2 of the magical devices, conduct a review, and identify areas of remaining work. | Kong Qiu | CA4000
BPRA1.2 | Business Processes As-Is Final | Finalize a final baseline of all the current business processes used to produce version 2 of the magical devices. | Kong Qiu | CA5000
BPRT1 | Business Process To-Be | Develop the to-be business processes to reflect the way we wish the new facility to perform. | Kong Qiu | CA6000
BPRT1.1 | Business Processes To-Be Draft | Prepare the new set of business processes to produce version 3 of the magical devices, conduct a review, and identify areas of remaining work. | Kong Qiu | CA7000
BPRT1.2 | Business Processes To-Be Final | Finalize a final baseline of the new set of business processes to produce version 3 of the magical devices. | Kong Qiu | CA8000
GAN1 | Gap Analysis | Perform a gap analysis to determine what work is needed to implement the to-be processes. | Kong Qiu | CA9000
GAN1.1 | Gap Analysis Draft | Prepare an analysis of the changes between the as-is and to-be business processes, and the elements that will need to be created or modified to meet the to-be processes, conduct a review, and identify areas of remaining work. | Kong Qiu | CA10000
GAN1.2 | Gap Analysis Final | Prepare a final analysis of the changes between the as-is and to-be business processes, and the elements that will need to be created or modified to meet the to-be processes. | Kong Qiu | CA11000
SYS1 | System | Develop the top-level system architecture, the system test plan and system test procedures, and build the integrated hardware and software system that will produce the magical devices version 3. | Mary Sperling | CA12000
SYA1 | System Architecture | Develop the top-level system architecture documenting the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3. | Mary Sperling | CA13000
SYA1.1 | System Architecture Draft | Prepare a draft system architecture of the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA14000
SYA1.2 | System Architecture Final | Prepare a final system architecture baseline of the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3. | Mary Sperling | CA15000
SYTP1 | System Test Planning | Develop the system test plan and test procedures to be used to validate the working system. | Mary Sperling | CA16000
SYTP1.1 | System Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the system. | Mary Sperling | CA17000
SYTP1.2 | System Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the system and verify it meets the system requirements, conduct a review, and identify areas of remaining work. | Mary Sperling | CA18000
SYTP1.3 | System Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the system and verify it meets the system requirements, conduct a review, and identify areas of remaining work. | Mary Sperling | CA19000
SYTP1.4 | System Test Procedures Final | Prepare a final baseline of the procedures to be used to test the system and verify it meets the system requirements. | Mary Sperling | CA20000
SYB1 | System Build | Build the integrated hardware and software system. | Mary Sperling | CA21000
SYB1.1 | System Build 1 | Build the first version of the system to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA22000
SYB1.2 | System Build 2 | Build the second version of the system to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA23000
SYB1.3 | System Build Final | Build the final version of the system to be used to produce the magical devices version 3. | Mary Sperling | CA24000
HW1 | Hardware | Refine the hardware detailed requirements, document a hardware development plan, prepare the hardware design, develop the hardware test plan and test procedures to be used for validation, and build the production lines of hardware equipment to produce the magical devices version 3. | Andre Young | CA25000
HWP1 | Hardware Planning | Develop the hardware detailed requirements and a hardware development plan. | Andre Young | CA26000
HWP1.1 | Hardware Detailed Requirements | Prepare detailed hardware requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for hardware design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Andre Young | CA27000
HWP1.2 | Hardware Development Plan | Prepare a hardware development plan documenting the processes, personnel, facilities, and schedule required to develop the hardware solution. | Andre Young | CA28000
HWD1 | Hardware Design | Prepare the design for the hardware to produce the magical devices version 3. | Andre Young | CA29000
HWD1.1 | Hardware Design Draft 1 | Prepare a first draft of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA30000
HWD1.2 | Hardware Design Draft 2 | Prepare a second draft of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA31000
HWD1.3 | Hardware Design Final | Prepare a final baseline of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3. | Andre Young | CA32000
HWTP1 | Hardware Test Planning | Develop the hardware test plan and test procedures to be used to validate the working system. | Andre Young | CA33000
HWTP1.1 | Hardware Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the hardware. | Andre Young | CA34000
HWTP1.2 | Hardware Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements, conduct a review, and identify areas of remaining work. | Andre Young | CA35000
HWTP1.3 | Hardware Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements, conduct a review, and identify areas of remaining work. | Andre Young | CA36000
HWTP1.4 | Hardware Test Procedures Final | Prepare a final baseline of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements. | Andre Young | CA37000
HWB1 | Hardware Build | Procure the equipment, and build the hardware to produce the magical devices version 3. | Andre Young | CA38000
HWB1.1 | Hardware Procurement | Finalize all remaining hardware procurement not already in-house due to early procurement as the design was developed. As the system architecture and the hardware design are finalized, this item will be refined into greater detail to break out the individual elements of equipment required for staging, piece build, assembly, finishing, QA, management stations, control stations, and magic dust. | Andre Young | CA39000
HWB1.2 | Hardware Build 1 | Build the first version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA40000
HWB1.3 | Hardware Build 2 | Build the second version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA41000
HWB1.4 | Hardware Build 3 | Build the third version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA42000
HWB1.5 | Hardware Build Final | Baseline the final version of the hardware to be used to produce the magical devices version 3. | Andre Young | CA43000
SW1 | Software | Refine the software detailed requirements, document a software development plan, prepare the software design, develop the software test plan and test procedures to be used for validation, and build the software to produce the magical devices version 3. | Byomkesh Bakshi | CA44000
SWP1 | Software Planning | Develop the software detailed requirements and a software development plan. | Byomkesh Bakshi | CA45000
SWP1.1 | Software Detailed Requirements | Prepare detailed software requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for software design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Byomkesh Bakshi | CA46000
SWP1.2 | Software Development Plan | Prepare a software development plan documenting the processes, personnel, facilities, and schedule required to develop the software solution. | Byomkesh Bakshi | CA47000
SWD1 | Software Design | Prepare the design for the software to produce the magical devices version 3. | Byomkesh Bakshi | CA48000
SWD1.1 | Software Design Draft 1 | Prepare a first draft of the software design to meet all the detailed software requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA49000
SWD1.2 | Software Design Draft 2 | Prepare a second draft of the software design to meet all the detailed software requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA50000
SWD1.3 | Software Design Final | Prepare a final baseline of the software design to meet all the detailed software requirements and produce the magical devices version 3. | Byomkesh Bakshi | CA51000
SWTP1 | Software Test Planning | Develop the software test plan and test procedures to be used to validate the working system. | Byomkesh Bakshi | CA52000
SWTP1.1 | Software Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the software. | Byomkesh Bakshi | CA53000
SWTP1.2 | Software Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the software and verify it meets the detailed software requirements, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA54000
SWTP1.3 | Software Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the software and verify it meets the detailed software requirements, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA55000
SWTP1.4 | Software Test Procedures Final | Prepare a final baseline of the procedures to be used to test the software and verify it meets the detailed software requirements. | Byomkesh Bakshi | CA56000
SWB1 | Software Build | Procure off-the-shelf software, and build the software to produce the magical devices version 3. | Byomkesh Bakshi | CA57000
SWB1.1 | Software Procurement | Finalize all remaining software procurement for not already in-house due to early procurement as the design was developed. As the system architecture and the software design are finalized, this item will be refined to break out the individual elements of software required for the production equipment, management stations, and control stations. | Byomkesh Bakshi | CA58000
SWB1.2 | Software Sprint 1 | Develop the first iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA59000
SWB1.3 | Software Sprint 2 | Develop the second iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA60000
SWB1.4 | Software Sprint 3 | Develop the third iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA61000
SWB1.5 | Software Sprint 4 | Develop the fourth iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA62000
SWB1.6 | Software Sprint 5 | Develop the fifth iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA63000
SWB1.7 | Software Final | Baseline the final version of the software to be used to produce the magical devices version 3. | Byomkesh Bakshi | CA64000
SEC1 | Security | Refine the security detailed requirements, develop the security architecture, and develop the security test plan and test procedures to be used for validation and certification of the secure system. | Cathy Kerr | CA65000
SECD1 | Security Design | Refine the security detailed requirements and develop the security architecture to be used to secure the system. | Cathy Kerr | CA66000
SECD1.1 | Security Detailed Requirements | Prepare detailed security requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for security design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Cathy Kerr | CA67000
SECD1.2 | Security Architecture | Prepare a baseline security architecture of the hardware, software, processes, and functional components required to meet the detailed security requirements. | Cathy Kerr | CA68000
SECTP1 | Security Test Planning | Develop the security test plan and test procedures to be used for validation and certification of the secure system. | Cathy Kerr | CA69000
SECTP1.1 | Security Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct security testing of the system. | Cathy Kerr | CA70000
SECTP1.2 | Security Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the system and verify it meets the detailed security requirements, conduct a review, and identify areas of remaining work. | Cathy Kerr | CA71000
SECTP1.3 | Security Test Procedures Final | Prepare a final baseline of the procedures to be used to test the system and verify it meets the detailed security requirements. | Cathy Kerr | CA72000
FAC1 | Facility | Refine the facility detailed requirements, document a facility build plan, prepare the facility design, put in place the procurement with the contractor building the external elements of the facility, and build the internal elements of the facility to produce the magical devices version 3. | Irwin Fletcher | CA73000
FACP1 | Facilities Planning | Develop the facility detailed requirements and a hardware development plan. | Irwin Fletcher | CA74000
FACP1.1 | Facilities Detailed Requirements | Prepare detailed facility requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for the facility design, build, and inspection, conduct a review, address any issues, and prepare a final baseline. | Irwin Fletcher | CA75000
FACP1.2 | Facilities Build Plan | Prepare a build plan documenting the processes, personnel, equipment, and schedule required to develop the production facility. | Irwin Fletcher | CA76000
FACD1 | Facilities Design | Prepare the design for the facility to produce the magical devices version 3. | Irwin Fletcher | CA77000
FACD1.1 | Facilities Design Draft 1 | Prepare a first draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA78000
FACD1.2 | Facilities Design Draft 2 | Prepare a second draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA79000
FACD1.3 | Facilities Design Draft 3 | Prepare a third draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA80000
FACD1.4 | Facilities Design Final | Prepare a final baseline of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3. | Irwin Fletcher | CA81000
FACB1 | Facilities Build | Put in place the procurement with the facilities contractor, and build the internal elements of the facility to produce the magical devices version 3. | Irwin Fletcher | CA82000
FACB1.1 | Facilities Procurement | Finalize all remaining facilities procurement not already in-house due to early procurement as the design was developed, and put the contract in place with the contractor building the external elements of the facility. As the facilities design is completed, this item will be refined to break out the individual elements of building material required to complete the facilities build. | Irwin Fletcher | CA83000
FACB1.2 | Facilities Build 1 | Build the first version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA84000
FACB1.3 | Facilities Build 2 | Build the second version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA85000
FACB1.4 | Facilities Build 3 | Build the third version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA86000
FACB1.5 | Facilities Build 4 | Build the fourth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA87000
FACB1.6 | Facilities Build 5 | Build the fifth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA88000
FACB1.7 | Facilities Build 6 | Build the sixth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA89000
FACB1.8 | Facilities Build 7 | Build the seventh version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA90000
FACB1.9 | Facilities Build Final | Build the final version of the facility to be used to produce the magical devices version 3. | Irwin Fletcher | CA91000
QA1 | Quality Assurance | Conduct the quality assurance to ensure the hardware, software, system, security, and facility are fully tested and inspected to meet all the requirements, are correctly configured, and will be of the highest quality and fit for purpose to produce the magical devices version 3. | Son Goku | CA92000
QAHW1 | Hardware Test | Conduct testing of the hardware to verify all the requirements are met. | Son Goku | CA93000
QAHW1.1 | Hardware Build 1 Test | Conduct testing of the first hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA94000
QAHW1.2 | Hardware Build 2 Test | Conduct testing of the second hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA95000
QAHW1.3 | Hardware Build 3 Test | Conduct testing of the third hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final baseline. | Son Goku | CA96000
QASW1 | Software Test | Conduct testing of the software to verify all the requirements are met. | Son Goku | CA97000
QASW1.1 | Software Sprint 1 Test | Conduct testing of the first software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA98000
QASW1.2 | Software Sprint 2 Test | Conduct testing of the second software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA99000
QASW1.3 | Software Sprint 3 Test | Conduct testing of the third software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA100000
QASW1.4 | Software Sprint 4 Test | Conduct testing of the fourth software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA101000
QASW1.5 | Software Sprint 5 Test | Conduct testing of the fifth software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final baseline. | Son Goku | CA102000
QASY1 | System Test | Conduct testing of the system to verify all the requirements are met. | Son Goku | CA103000
QASY1.1 | System Build 1 Test | Conduct testing of the first system build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA104000
QASY1.2 | System Build 2 Test | Conduct testing of the second system build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final build. | Son Goku | CA105000
QASC1 | System Certification | Conduct formal certification of the system to be ready to procure the magical devices version 3. | Son Goku | CA106000
QASC1.1 | System Certification | Review all the prior system, hardware, software, and security testing, validate the readiness for system operation, conduct any final certification activities required, and formally certify the system ready for production of the magical devices version 3. | Son Goku | CA107000
QASE1 | Security Test | Conduct formal security certification of the system to be ready to produce the magical devices version 3. | Son Goku | CA108000
QASE1.1 | Security Test Final | Conduct testing of the system to verify all the security requirements are met, conduct remediation of any deficiencies, and retest any areas required. | Son Goku | CA109000
QASEC1 | Security Certification | Conduct testing of the software to verify all the requirements are met. | Son Goku | CA110000
QASEC1.2 | Security Certification Final | Review the security testing, validate the readiness for secure operation, conduct any final certification activities required, and formally certify the system as secure for production of the magical devices version 3. | Son Goku | CA111000
FACI1 | Facilities Inspection | Conduct inspections of the facility to verify all the requirements and design are met. | Son Goku | CA112000
FACI1.1 | Inspection Build 1 | Conduct an inspection of the first facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA113000
FACI1.2 | Inspection Build 2 | Conduct an inspection of the second facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA114000
FACI1.3 | Inspection Build 3 | Conduct an inspection of the third facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA115000
FACI1.4 | Inspection Build 4 | Conduct an inspection of the fourth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA116000
FACI1.5 | Inspection Build 5 | Conduct an inspection of the fifth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA117000
FACI1.6 | Inspection Build 6 | Conduct an inspection of the sixth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA118000
FACI1.7 | Inspection Build 7 | Conduct an inspection of the seventh facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final build. | Son Goku | CA119000
IMP1 | Implementation | Prepare and manage a comprehensive implementation plan to ensure the success of a multi-phase pilot and rollout of the production system to produce the magical devices version 3. | Heidi Geis | CA120000
IMPP1 | Implementation Planning | Prepare an implementation plan documenting the processes, personnel, facilities, and schedule required to implement the production system. | Heidi Geis | CA121000
IMPP1.1 | Implementation Plan Draft 1 | Prepare a first draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA122000
IMPP1.2 | Implementation Plan Draft 2 | Prepare a second draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA123000
IMPP1.3 | Implementation Plan Draft 3 | Prepare a third draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA124000
IMPP1.4 | Implementation Plan Draft 4 | Prepare a fourth draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA125000
IMPP1.5 | Implementation Plan Final | Prepare a final baseline of the implementation plan for a three phase pilot and rollout of the production system. | Heidi Geis | CA126000
IMPP1.6 | Implementation Readiness Review | Review the system certification, security certification, facilities inspections, implementation plan, training material, and support package to determine readiness for progress to implementation. | Heidi Geis | CA127000
IMPH1 | Implementation Phase 1 | Conduct a pilot and rollout of phase 1 of the system. | Heidi Geis | CA128000
IMPH1.1 | Phase 1 Pilot | Pilot the first production line, ramping up to full capacity. | Heidi Geis | CA129000
IMPH1.2 | Phase 1 Rollout | Rollout full capacity of the first production line. | Heidi Geis | CA130000
IMPH2 | Implementation Phase 2 | Conduct a pilot and rollout of phase 2 of the system. | Heidi Geis | CA131000
IMPH2.1 | Phase 2 Pilot | Pilot the second production line, ramping up to full capacity. | Heidi Geis | CA132000
IMPH2.2 | Phase 2 Rollout | Rollout full capacity of the second production line. | Heidi Geis | CA133000
IMPH3 | Implementation Phase 3 | Conduct a pilot and rollout of phase 3 of the system. | Heidi Geis | CA134000
IMPH3.1 | Phase 3 Pilot | Pilot the third production line, ramping up to full capacity. | Heidi Geis | CA135000
IMPH3.2 | Phase 3 Rollout | Rollout full capacity of the third production line. | Heidi Geis | CA136000
TR1 | Training | Refine the training detailed requirements, develop a training plan, and prepare the material to train the users of the production system, and train the teams. | Jean Cunliffe | CA137000
TRP1 | Training Planning | Refine the training detailed requirements and document a training plan to train the users of the production system. | Jean Cunliffe | CA138000
TRP1.1 | Training Detailed Requirements | Prepare detailed training requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture. | Jean Cunliffe | CA139000
TRP1.2 | Training Plan | Prepare a plan documenting the processes, personnel, facilities, and schedule required to develop the training solution. | Jean Cunliffe | CA140000
TRM1 | Training Material | Prepare the material to train the users of the production system. | Jean Cunliffe | CA141000
TRM1.1 | Training Material Draft 1 | Prepare the first draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA142000
TRM1.2 | Training Material Draft 2 | Prepare the second draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA143000
TRM1.3 | Training Material Draft 3 | Prepare the third draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA144000
TRM1.4 | Training Material Final | Prepare the final baseline of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA145000
TRPH1 | Training Phases | Conduct three phases of training for the pilots and rollout of the production system. | Jean Cunliffe | CA146000
TRPH1.1 | Phase 1 Training | Train the team in use of the first production line for producing the magical devices version 3. | Jean Cunliffe | CA147000
TRPH1.2 | Phase 2 Training | Train the team in use of the second production line for producing the magical devices version 3. | Jean Cunliffe | CA148000
TRPH1.3 | Phase 3 Training | Train the team in use of the third production line for producing the magical devices version 3. | Jean Cunliffe | CA149000
SU1 | Support | Refine the support detailed requirements, develop a support plan, prepare the package of documentation and processes to support the system and facilities, and transition support to the operations teams. | Henry Kiku | CA150000
SUP1 | Support Planning | Refine the support detailed requirements and document a support plan to support the system and facilities to produce the magical devices version 3. | Henry Kiku | CA151000
SUP1.1 | Support Detailed Requirements | Prepare detailed support requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, conduct a review, address any issues, and prepare a final baseline. | Henry Kiku | CA152000
SUP1.2 | Support Plan | Prepare a support plan documenting the processes, personnel, facilities, and schedule required to develop the support solution. | Henry Kiku | CA153000
SUPA1 | Support Package | Prepare the package of documentation and processes to support the system and facilities to produce the magical devices version 3. | Henry Kiku | CA154000
SUPA1.1 | Support Package Draft 1 | Prepare the first version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA155000
SUPA1.2 | Support Package Draft 2 | Prepare the second version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA156000
SUPA1.3 | Support Package Draft 3 | Prepare the third version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA157000
SUPA1.4 | Support Package Final | Prepare the final version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA158000
SUPS1 | Phase Support | Transition support to the operations teams. | Henry Kiku | CA159000
SUPS1.1 | Phase 1 Support Transition | Transition support of the first production line from the development team to the operations support team. | Henry Kiku | CA160000
SUPS1.2 | Phase 2 Support Transition | Transition support of the second production line from the development team to the operations support team. | Henry Kiku | CA161000
SUPS1.3 | Phase 3 Support Transition | Transition support of the third production line from the development team to the operations support team. | Henry Kiku | CA162000
PM1 | Project Management | Establish the project management office to manage the project as it progresses through execution and closing, hold a kick-off meeting to coordinate all members of the project, manage the risk budget, and conduct the activities required to successfully close out the project. | Charles Wallace | CA163000
PMA1 | Project Management Activities | Establish the project management office to manage the project as it progresses, and hold a kick-off meeting to coordinate all members of the project. | Charles Wallace | CA164000
PMA1.1 | Project Management Office | The project manager, project scheduler, and project coordinator for the entire project. | Charles Wallace | CA165000
PMA1.2 | Kick-off Meeting | Assemble the full team to review the project plan, answer any questions, identify any unknown issues, conduct some team building, and set a coordinated foundation for the rest of the project. As per the risk management plan, 70% of the anticipated requirement for Magic Dust will also be procured on the first day of the project. | Charles Wallace | CA166000
PMRB1 | Risk Budget | Manage the risk budget to minimize the risks to the project budget and schedule performance. | Charles Wallace | CA167000
PMRB1.1 | Risk Buffer | Provide a risk buffer of time and cost to protect the pilot and rollout dates once the project plan is approved. | Charles Wallace | CA168000
PMC1 | Project Closure | Conduct the activities required to close out the project. | Charles Wallace | CA169000
PMC1.1 | Project Closure Readiness Review | Review the status of all previous elements of the project, and assure readiness for project closure. | Charles Wallace | CA170000
PMC1.2 | Final Procurements Closure | Review the production line rollouts, support, and all remaining open procurements, resolve any outstanding issues, and conduct formal closure. | Charles Wallace | CA171000
PMC1.3 | Lessons Learned Meeting | Review all lessons learned documentation collected during the project, conduct a final lessons learned all team meeting, and assemble a final set of lessons learned. | Charles Wallace | CA172000
PMC1.4 | Lessons Learned Report | Prepare a final lessons learned report, send it to all stakeholders, and flow recommended actions to the relevant parts of the organizations. | Charles Wallace | CA173000
PMC1.5 | Project Final Report | Prepare a project final report, documenting what happened with scope, time, cost, the business case, major risks, major lessons learned, and recommendations for next steps. | Charles Wallace | CA174000

## WBS ID check
WBS ID | Check formula: =IF(A6=A5,"DUPLICATE","OK")
BPR1 | OK
BPRA1 | OK
BPRA1.1 | OK
BPRA1.2 | OK
BPRT1 | OK
BPRT1.1 | OK
BPRT1.2 | OK
FAC1 | OK
FACB1 | OK
FACB1.1 | OK
FACB1.2 | OK
FACB1.3 | OK
FACB1.4 | OK
FACB1.5 | OK
FACB1.6 | OK
FACB1.7 | OK
FACB1.8 | OK
FACB1.9 | OK
FACD1 | OK
FACD1.1 | OK
FACD1.2 | OK
FACD1.3 | OK
FACD1.4 | OK
FACI1 | OK
FACI1.1 | OK
FACI1.2 | OK
FACI1.3 | OK
FACI1.4 | OK
FACI1.5 | OK
FACI1.6 | OK
FACI1.7 | OK
FACP1 | OK
FACP1.1 | OK
FACP1.2 | OK
GAN1 | OK
GAN1.1 | OK
GAN1.2 | OK
HW1 | OK
HWB1 | OK
HWB1.1 | OK
HWB1.2 | OK
HWB1.3 | OK
HWB1.4 | OK
HWB1.5 | OK
HWD1 | OK
HWD1.1 | OK
HWD1.2 | OK
HWD1.3 | OK
HWP1 | OK
HWP1.1 | OK
HWP1.2 | OK
HWTP1 | OK
HWTP1.1 | OK
HWTP1.2 | OK
HWTP1.3 | OK
HWTP1.4 | OK
IMP1 | OK
IMPH1 | OK
IMPH1.1 | OK
IMPH1.2 | OK
IMPH2 | OK
IMPH2.1 | OK
IMPH2.2 | OK
IMPH3 | OK
IMPH3.1 | OK
IMPH3.2 | OK
IMPP1 | OK
IMPP1.1 | OK
IMPP1.2 | OK
IMPP1.3 | OK
IMPP1.4 | OK
IMPP1.5 | OK
IMPP1.6 | OK
MDV3 | OK
PM1 | OK
PMA1 | OK
PMA1.1 | OK
PMA1.2 | OK
PMC1 | OK
PMC1.1 | OK
PMC1.2 | OK
PMC1.3 | OK
PMC1.4 | OK
PMC1.5 | OK
PMRB1 | OK
PMRB1.1 | OK
QA1 | OK
QAHW1 | OK
QAHW1.1 | OK
QAHW1.2 | OK
QAHW1.3 | OK
QASC1 | OK
QASC1.1 | OK
QASE1 | OK
QASE1.1 | OK
QASEC1 | OK
QASEC1.2 | OK
QASW1 | OK
QASW1.1 | OK
QASW1.2 | OK
QASW1.3 | OK
QASW1.4 | OK
QASW1.5 | OK
QASY1 | OK
QASY1.1 | OK
QASY1.2 | OK
SEC1 | OK
SECD1 | OK
SECD1.1 | OK
SECD1.2 | OK
SECTP1 | OK
SECTP1.1 | OK
SECTP1.2 | OK
SECTP1.3 | OK
SU1 | OK
SUP1 | OK
SUP1.1 | OK
SUP1.2 | OK
SUPA1 | OK
SUPA1.1 | OK
SUPA1.2 | OK
SUPA1.3 | OK
SUPA1.4 | OK
SUPS1 | OK
SUPS1.1 | OK
SUPS1.2 | OK
SUPS1.3 | OK
SW1 | OK
SWB1 | OK
SWB1.1 | OK
SWB1.2 | OK
SWB1.3 | OK
SWB1.4 | OK
SWB1.5 | OK
SWB1.6 | OK
SWB1.7 | OK
SWD1 | OK
SWD1.1 | OK
SWD1.2 | OK
SWD1.3 | OK
SWP1 | OK
SWP1.1 | OK
SWP1.2 | OK
SWTP1 | OK
SWTP1.1 | OK
SWTP1.2 | OK
SWTP1.3 | OK
SWTP1.4 | OK
SYA1 | OK
SYA1.1 | OK
SYA1.2 | OK
SYB1 | OK
SYB1.1 | OK
SYB1.2 | OK
SYB1.3 | OK
SYS1 | OK
SYTP1 | OK
SYTP1.1 | OK
SYTP1.2 | OK
SYTP1.3 | OK
SYTP1.4 | OK
TR1 | OK
TRM1 | OK
TRM1.1 | OK
TRM1.2 | OK
TRM1.3 | OK
TRM1.4 | OK
TRP1 | OK
TRP1.1 | OK
TRP1.2 | OK
TRPH1 | OK
TRPH1.1 | OK
TRPH1.2 | OK
TRPH1.3 | OK