## Slide 1
Business Processes To-Be Final
Business Processes As-Is Final
Business Processes To-Be
Draft
Business Processes As-Is Draft
Implement-ation Readiness Review
Implement-ation Plan Final
Training Material Final
Support Package Final
Facilities Build Final
System
Build 1
Implement-ation Plan Draft 3
Training Material
Draft 2
Support Package Draft 2
Facilities Build 4
Inspection Build 6
Security Test
Security Certification
Implement-ation Plan Draft 4
Training Material
Draft 3
Support Package Draft 3
Facilities Build 7
F
System Architecture Draft
Kickoff Meeting
Gap Analysis
Draft
Gap Analysis
Final
System Architecture Final
S
Phase 1
Pilot
Phase 2 Training
Security
Test Plan
Software
Test Plan
Hardware
Test Plan
Facilities Design
Draft 1
Software
Design
Draft 1
Phase 1 Rollout
Phase 3 Training
Phase 2
Pilot
Software Test Procedures
Draft 1
Hardware Design
Draft 1
Software
Design
Draft 2
Phase 1 Support
Phase 3
Pilot
Phase 2 Rollout
Software Test Procedures
Draft 2
Hardware Test Procedures Draft 1
Facilities Design
Draft 2
Hardware Design
Draft 2
Software
Design
Final
Phase 3 Rollout
Phase 2 Support
Software Test Procedures
Final
System Test Procedures
Draft 1
Hardware Test Procedures Draft 2
Facilities Design
Draft 3
Hardware Design
Final
Software Procurement
Phase 3 Support
System Test Procedures
Draft 2
Hardware Test Procedures Final
Implement-ation Plan Draft 2
Training Material
Draft 1
Support Package Draft 1
Facilities Design
Final
Hardware Procurement
Software
Sprint 1
Final Procuremnts Closure
Security Test Procedures Final
Facilities Build 1
Hardware Build 1 Test
Software
Sprint 2
Lessons Learned
Report
Facilities Build 2
Hardware Build 2 Test
Software
Sprint 3
Software
Final
Magical Devices Version 3 (MDV3)
Project Precedence Diagram
Security Detailed Requiremnts
System
Test Plan
Implement-ation Plan
Draft 1
Training Detailed Requiremnts
Support Detailed Requiremnts
Facilities Detailed Requiremnts
Hardware Detailed Requiremnts
Software
Detailed Requiremnts
Risk Buffer
Project Closure Readiness Review
Security Test Procedures Draft
System Test Procedures
Final
Hardware Build 1
Software Sprint 1 Test
Facilities Procurement
Phase 1 Training
Security Architecture
Facilities Build Plan
Hardware Dev Plan
Software
Dev Plan
Phase 1
Training
Training
Plan
Support Plan
Software
Sprint 4
Hardware Build 3 Test
Facilities Build 3
Lessons Learned
Meeting
Hardware Build 2
Software Sprint 2 Test
Inspection Build 1
Software Sprint 4 Test
Hardware Final
Inspection Build 3
System Build 1 Test
Inspection Build 4
System Certification
Inspection Build 7
System
Build 2
Facilities Build 5
System Build 2 Test
Inspection Build 5
System
Build Final
Facilities Build 6
Hardware Build 3
Software Sprint 3 Test
Inspection Build 2
Project
Final Report
Software Sprint 5 Test
Software Sprint 5