Project Management Plan

for the

Magical Devices Version 3 (MDV3)
Project

20YY-MM-DD

Prepared by:

Charles Wallace, Project Manager

Approved by:

Lucy Pevensie, President Magical Devices, Project Sponsor

This document provides a realistic example of a professional Project Management Plan

for a significantly sized $44M project with multiple domains.  Feel free to share this

document and the MDV3 project with anyone you wish.  Let’s help everyone.

The Project Management Plan should focus on project planning, not detailed planning.  It should define all the work required during execution, include it in the plan, and leave all further work for the execution stage once the plan is approved.  On a project of this size, there would probably be lower level plans for each of the domain areas: system, hardware, software, security, facilities, implementation, training, support.  This top level Project Management Plan provides the level of information the Sponsor needs to make any final decisions about trade-offs between scope, schedule, and budget before approving moving forward to execution, and the information the Project Manager needs to successfully monitor and control the project once underway.  Experience has shown that when the PM planning best practices are carried out they

will almost always produce a plan with a schedule and budget accuracy within +/- 10%.

Contents

1.	Executive Summary	1

1.1	Need	1

1.2	Sponsor	1

1.3	Customer	1

1.4	Business Case	3

1.4.1	Options	3

1.4.2	Assumptions	3

1.4.3	Benefits	4

1.4.4	Costs	4

1.4.5	Analysis	5

2.	Scope	6

2.1	Objective	7

2.2	Requirements	8

2.3	Solution	9

2.4	Work Breakdown Structure	10

2.4.1	Full WBS	11

2.4.2	Business Process	12

2.4.3	System	13

2.4.4	Hardware	14

2.4.5	Software	15

2.4.6	Security	16

2.4.7	Facility	17

2.4.8	Quality Assurance	18

2.4.9	Implementation	19

2.4.10	Training	20

2.4.11	Support	21

2.4.12	Project Management	22

2.5	Scope Verification	23

3.	Schedule	24

3.1	Precedence Diagram	25

3.2	Gantt Schedule	26

3.3	Critical Path	30

3.4	Milestones	32

4.	Budget	34

4.1	Deliverable Costs	34

4.2	Resource Costs	36

4.3	Cost Curve	37

5.	Risks	38

5.1	Risk Management Process	38

5.2	Risk Register	39

6.	Issues	47

7.	Stakeholders	48

8.	Resources	50

8.1	Project Team	50

8.2	Resource Loading	53

8.3	Critical Resources	53

8.3.1	Software Engineers	53

8.3.2	Magic Dust	54

9.	Communications	55

9.1	Weekly Issue Status Meetings	55

9.2	Monthly Project Review Meetings	55

9.3	Change Control Board Meetings	56

9.4	Monthly Company Updates	56

9.5	Mayor Of Oakville Updates	56

9.6	Executive Director Magical Management Institute Updates	56

9.7	Facility Opening Press Conference	57

10.	Quality	58

10.1	Peer Reviews	58

10.1.1	Informal Peer Reviews.	58

10.1.2	Formal Peer Reviews	59

10.2	User Reviews	60

11.	Procurement	62

11.1	Facility	62

11.2	Building Material	62

11.3	Hardware Equipment	63

11.4	Magic Dust	63

11.5	Management Station & Control Station Hardware	63

11.6	Management Station Software	63

11.7	Control Station Software	63

12.	Change Control Process	64

Appendix A - Requirements	66

Appendix B - Work Breakdown Structure Dictionary	71

Appendix C - Project Issues List Format	87

Appendix D - Monthly Project Report Format	88

Appendix E - User Review Template	89

Appendix F - Change Request Form	90

List of Figures

Figure 1 – Top-Level Facility Diagram	9

Figure 2 - Work Breakdown Structure (Full)	11

Figure 3 - Work Breakdown Structure (Top-Level)	11

Figure 4 - Business Process Work	12

Figure 5 - System Work	13

Figure 6 - Hardware Work	14

Figure 7 - Software Work	15

Figure 8 - Security Work	16

Figure 9 - Facility Work	17

Figure 10 - Quality Assurance Work	18

Figure 11 - Implementation Work	19

Figure 12 - Training Work	20

Figure 13 - Support Work	21

Figure 14 - Project Management Work	22

Figure 15 - Precedence Diagram	25

Figure 16 - Gantt Schedule (Full)	27

Figure 17 - Gantt Schedule (Summary Tasks)	28

Figure 18 - Gantt Schedule (Calendar Order)	29

Figure 19 – Gantt Schedule (Critical Path)	30

Figure 20 - Gantt Schedule (Milestones)	32

Figure 21 - Cumulative Cost Curve	37

Figure 22 - Project Organization	50

Figure 23 - Resource Loading	53

List of Tables

Table 1 - Project Benefits	4

Table 2 - Project Costs	5

Table 3 - Project BCR and ROI	5

Table 4 - Critical Path Deliverables	31

Table 5 - Project Milestones	33

Table 6 – Major Deliverable Costs	35

Table 7 – Resource Costs By Type	37

Table 8 - Risk Register	46

Table 9 - Stakeholder Register	49

Table 10 - Project Roles & Responsibilities	52

Table 11 - User Review Lead / Participation	60

Executive Summary

This document provides the project management plan for the Magical Devices Version 3 (MDV3) project, a major upgrade of the company manufacturing capability to help ensure Magical Devices continued success.  It documents the planning baselines for scope, schedule, budget, and risks, and provides additional information to assist the Project Manager and team in successful execution of the effort.

This project supports the following objective from the Magical Devices Strategic Plan: “Magical Devices shall ensure we have sufficient manufacturing capacity to produce the most advanced magical devices with the highest quality at the lowest cost to meet projected market demand for the next ten years”.

This is a living document and shall be updated by the Project Manager as needed throughout the course of the project.

Need

The project has been initiated to respond to the following need.  Magical Devices version 2 have been selling well for the past several years with excellent results.  However, recent innovations in the field of magic, together with the results from our research and development projects, indicate it is possible to increase the effectiveness of the devices by at least 60%.  At the same time, advances in magic manufacturing equipment and processes indicate that next generation devices could be produced at a cost at least 30% lower than with our current facility.

In addition, user demand for the version 2 devices has been growing at a rate of 20% a year.  Projections show that, even with the retrofits currently planned, the existing manufacturing facility will reach production capacity within 36 months.

Therefore, Magical Devices have identified an opportunity to build a new manufacturing facility capable of producing a more effective suite of magical devices that will generate even greater market demand, produced at a lower cost, and with capacity that combined with our existing facility will be able to meet anticipated demand for at least the following ten years.

Sponsor

Lucy Pevensie, President of Magical Devices, is the sponsor of this project, responsible for the project budget, and the authority for approval of this project plan and any changes during execution.

Customer

Three customer groups have been identified representing the end-users of the project, who participated in definition of the project scope, and will be responsible for sign-off of the requirements and acceptance of the final deliverables:

- Ava Lee, VP of Customer Satisfaction.  Represents the consumer end-users of the magic devices, and is responsible for ensuring the functional requirements for version 3 of the magical devices are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the final device configuration.

- Ezekiel Rawlins, Magical Devices VP Manufacturing.  Represents the production end-users of the project, and is responsible for ensuring the requirements for the production lines are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the final equipment and production line configuration.

- Dave Robicheaux, Magical Devices Director of Facilities & Operations.  Represents the facility and operations end-users of the project, and is responsible for ensuring the requirements for the facility are correctly and completely defined, coordination of related user reviews as the project progresses, and acceptance of the facility configuration and support programs.

Business Case

The business case analysis from initiation has been revised to reflect the results of project planning.  In summary, the planning stage analysis indicates the ROI turns positive in year 2, and is more than 600% in year 5.  This indicates the project will provide much more benefit than it costs, and so it has been prioritized for investment by the Magical Devices Board of Directors and approved for proceeding to execution by the Project Sponsor.

More information on the options considered, assumptions, constraints, costs, benefits, and analysis can be found in the following sections.

Options

Three options were examined:

- Upgrade the current manufacturing facility.  This option was not chosen because the costs were estimated to be prohibitive, it would interrupt current production, and it would not be possible to build the capacity for expected growth in the market in the current space.

- Outsource production to third party providers.  This option was not selected because there is currently no critical mass of suppliers producing magical devices enabling competitive outsourcing, and it was judged to not be possible with an outsourced model to innovate enhancements as quickly as required to stay competitive in the new and rapidly changing magical devices segment.

- Build a new manufacturing facility.  This option was selected since it would not interrupt current production, it would allow the most rapid in-house innovation to respond to market input as version 4 and later devices are developed, and it provided the greatest five year economic benefit.

Assumptions

The business case is based on the following assumptions:

- The feasibility study and pilot projects conducted by the Research and Development department indicates it is possible to build version 3 magical devices with an at least 60% increase in effectiveness over version 2.

- The marketing study and analysis conducted by the Business Development department indicates that version 3 magical devices with 60% greater effectiveness will generate a doubling of current year over year growth in market demand to 40%.

- The research and pilot projects conducted by the manufacturing department indicate updated processes and equipment can reduce the production cost (manufacturing and operating) per device by at least 30%.

- Marketing costs of $20 per unit and revenue of $100 per unit will not change.

- The costs for developing the new facility will be 15% greater per square meter than experienced for the build of the version 2 facility.  A new facility of size 5,000 square meters will be needed to meet the anticipated growth in demand over the next five years.

- The costs for the hardware, software, project personnel, and project management costs will be 50% greater than experienced for build of the version 2 facility.

- This project does not need to consider decommissioning and sell-off of the version 2 equipment.  It is assumed the current facility will be kept in operation for manufacture of version 2 devices for the secondary market for at least two years following open of the version 3 facility, following which a separate project will address retrofit of the version 2 facility to meet the additional demand for version 3 devices in years six through ten.

Benefits

The benefits of the project are defined by the additional profit to be obtained from the new facility, calculated as the difference between the profits from the version 3 facility and the profits from continued use of the version 2 facility.  The following table estimates the production level, production costs, marketing costs, revenue, and profit for the current manufacturing facility, the new manufacturing facility, and the difference over five years.  The current facility reaches maximum production capacity in year 3.

| Year | 1 | 2 | 3 | 4 | 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Current Manufacturing Facility |  |  |  |  |  |  |
| Production (M) @ growth of 20% | 0.7 | 0.84 | 1.01 | 1.01 | 1.01 | 4.56 |
| Cost (M) @ $60 / unit | $42 | $50 | $60 | $60 | $60 | $274 |
| Marketing costs (M) @ $20 / unit | $14 | $17 | $20 | $20 | $20 | $91 |
| Revenue @ $100 / unit | $70 | $84 | $101 | $101 | $101 | $456 |
| Profit (M) | $14 | $17 | $20 | $20 | $20 | $91 |
| 2. New manufacturing facility |  |  |  |  |  |  |
| Production (M) @ growth of 40% | 1. | 1.4 | 1.96 | 2.74 | 3.84 | 10.95 |
| Cost (M) @ $42 / unit | $42 | $59 | $82 | $115 | $161 | $460 |
| Marketing costs (M) @ $20 / unit | $20 | $28 | $39 | $55 | $77 | $219 |
| Revenue @ $100 / unit | $100 | $140 | $196 | $274 | $384 | $1,095 |
| Profit (M) | $38 | $53 | $74 | $104 | $146 | $416 |
| 3. Difference |  |  |  |  |  |  |
| Production (M) | 0.3 | 0.56 | 0.95 | 1.74 | 2.83 | 6.38 |
| Cost (M) | $0 | $8 | $22 | $55 | $101 | $186 |
| Marketing costs (M) | $6 | $11 | $19 | $35 | $57 | $128 |
| Revenue | $30 | $56 | $95 | $174 | $283 | $638 |
| Profit (M) | $24 | $36 | $54 | $84 | $126 | $325 |

Table 1 - Project Benefits

Costs

Compared to the initiation stage business case estimate, the planning estimate has lower costs for the facility, building materials, production equipment, management station hardware, control station software, project personnel, and project management personnel.  It has higher costs for the control station hardware, management station software, magic dust, and risk budget.  There is a new cost in planning for a security consultant to mitigate the security certification risk as described in the risk management plan.  Overall, the planning estimate costs are approximately 6% lower than estimated during initiation.

The following table summarizes the costs to build the new facility based on the plan described in this document.

| 1. Facility Procurement |  |
| --- | --- |
| Number of square meters of factory space | 5000 |
| Cost per square meter of factory space | $1,850 |
| Total | $9,250,000 |
| 2. Building Material |  |
| All facility internal materials | $565,000 |
| Total | $565,000 |
| 3. Hardware Procurement |  |
| Number of production lines | 3 |
| Hardware cost per production line | $3,000,000 |
| Management station | $100,000 |
| Control station | $200,000 |
| Magic dust | $777,000 |
| Total | $10,477,000 |
| 4. Software Procurement |  |
| Number of production lines | 3 |
| Cost per production line | $1,100,000 |
| Management station | $200,000 |
| Control station | $300,000 |
| Total | $4,400,000 |
| 5. Project Personnel |  |
| Project leads | $3,283,000 |
| Project team | $9,680,000 |
| Security consultant | $66,400 |
| Total | $13,029,400 |
| 6. Project Management |  |
| Project management team | $1,695,960 |
| Risk budget | $5,050,000 |
| Total | $6,745,960 |
| Total Project Costs | $44,467,360 |

Table 2 - Project Costs

Analysis

The expected additional profit was compared to the project costs, and the benefit / cost ratio (BCR) and return on investment (ROI) calculated over five years, as shown in the table below.

| Year | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Cumulative additional profit (M) | $24 | $60 | $115 | $199 | $325 |
| Benefit / Cost Ratio (BCR) | 0.54 | 1.36 | 2.58 | 4.47 | 7.3 |
| Return on investment (ROI) | -46% | 36% | 158% | 347% | 630% |

Table 3 - Project BCR and ROI

This analysis shows the project provides much more benefit than it costs, and so it has been prioritized for investment by the Magical Devices Board of Directors and approved for proceeding to execution by the Project Sponsor.

Scope

This section describes the MDV3 project scope, including the project objective, assumptions, constraints, requirements, and the work breakdown structure defining all the deliverables to be produced during the project execution and closing.  It also describes the process to be used for scope verification.

All planning of the project schedule, budget, and risks described in the remainder of this document is based on this scope definition.

Additional information on each scope area can be found in subsidiary planning documents for each domain, including the System Management Plan, Hardware Management Plan, Software Management Plan, Security Management Plan, Facility Management Plan, Quality Management Plan, Implementation Management Plan, Training Management Plan, and Support Management Plan.  (Note: These lower level domain documents are not included with the MDV3 PM example.)

The current status of scope progress shall be reported each month to the Sponsor, Customer, and other relevant Stakeholders at the Monthly Project Review described in Section 9.2 – Monthly Project Review Meetings.

Any changes to the project scope once this plan is approved and baselined must go through the formal change control process described in Section 12 – Change Control Process.

Objective

The MDV3 project objective is:

- Develop a manufacturing facility capable of producing a version 3 release of Magical Devices with 60% greater effectiveness, at 30% less cost, able to meet demand growing by 40% a year for the next five years, by the end of fiscal year 20YY.

The project assumptions are:

- The site acquired last year adjacent to our current facility has sufficient space, power, water, and other resources required for development of the new facility.

- Office staff shall remain in the current facility, and the two facilities shall be connected by an enclosed walkway.

- This project does not need to consider staffing requirements since the Magical Devices human resources department will provide all required personnel as part of their existing growth plans.

The project constraints are:

- The budget for this project must not exceed the planned budget of $ $44,467,360.

- The total schedule for the project must not exceed the planned schedule of 32 months.

- Pilot operation of the first production line must begin within 25 months from project start.

- The manufacturing system must fully comply with all requirements of the Magical Management Institute (MMI) industry standard Secure Magical Device Manufacturing (MMI-321123-G).

Requirements

The MDV3 project requirements provide the scope detail required to build the Magical Devices Version 3 facility to achieve the project objective.  The requirements identify what the project needs to meet the objective, not how it will be done.  The “how” will be defined during project execution as the detailed requirements and design deliverables are developed.

Requirements have been identified in the areas of functionality, facility, equipment, management station, control station, supportability, regulatory, capacity, availability, environmental, security, training, marketing, and procurement.  A complete requirements listing can be found in Appendix A, along with the owner of the requirement and preliminary deliverable and test case allocations to be refined as the design and test planning is progressed during execution.

The requirements were gathered and baselined by the Magical Devices business analysts, based on experience with build of the Magical Devices Version 2 facility, extensive interviewing with the customer user groups, and research of relevant industry standards.  The requirements have gone through multiple rounds of review to ensure they are complete, consistent, and testable, and have been signed off by the respective owners.

Solution

The solution to be developed to meet the project objective is a new manufacturing facility that meets all the project requirements and uses the most modern and efficient production methods, new business processes, the most recent equipment hardware, and enhanced software capable of producing version 3 magical devices implementing the features made possible by the innovations developed by our research and development lab.

A top-level facility diagram is provided below, showing the planned orientation of the production lines, control stations, management station, material staging, shipping line, equipment spares locker, tools cabinet, and loading dock.

Figure 1 – Top-Level Facility Diagram

This solution definition was developed at a sufficient level of detail that the planning team was able to prepare a project plan with a schedule and budget at a level of accuracy estimated to be +/- 10% for Sponsor review and approval for proceeding to execution.  The additional definition detail sufficient to build the complete solution will be developed during project execution with production of the system architecture, hardware design, software design, and facility design deliverables.

Work Breakdown Structure

The MDV3 work breakdown structure (WBS) provides the formal baseline of the full scope of the project.  The Project Manager and Leads conducted several iterations of planning to prepare the WBS.  The WBS documents all of the project deliverables, and captures all the work to be performed during the project.

The WBS is shown in the following sections.  More information can also be found in the WBS dictionary in Appendix B, providing a description, owner, and cost account for each deliverable, and in the attached document “MDV3 WBS Dictionary”.

The deliverables in the work breakdown structure can also be found flowcharted they will be done in precedence order in Section 3.1 – Precedence Diagram, and as scheduled across the calendar in Section 3.2 – Gantt Schedule.

Full WBS

The full MDV3 work breakdown structure is provided below, showing all the deliverables to be prepared during the project.  This diagram can be zoomed in for greater visibility in this Project Management Plan document Microsoft Word soft-copy.  The full sized diagram can also be found in the attached documents “MDV3 Work Breakdown Structure” in PowerPoint, and “MDV3 Work Breakdown Structure - PDF” in PDF format.

Figure 2 - Work Breakdown Structure (Full)

In order to ensure the work outputs have the highest quality and will be fit for purpose to meet the stakeholder expectations, almost all of the work has been planned along agile principles, and so produced in more than one draft or sprint or version.  Reviews are conducted as part of the work of each deliverable, and by formal test or inspection events between the iterations, to identify any issues or deficiencies well before completion of the work, and ensure the final deliverable satisfies all of the project requirements and will fully meet the stakeholder needs.

A summary of the top two levels of the work breakdown structure can be found below.  More information on the deliverables and work in each area can be found in the following sections.

Figure 3 - Work Breakdown Structure (Top-Level)

Business Process

The business process work to be performed during the MDV3 project will develop the baselines for the as-is business processes, the to-be business processes, and then perform a gap analysis to determine what work is needed to implement the to-be processes.

The business process deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 4 - Business Process Work

System

The system work to be performed during the MDV3 project will develop the top-level system architecture, the system test plan and system test procedures, and build the integrated hardware and software system that will produce the Magical Devices Version 3.

The system deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 5 - System Work

Hardware

The hardware work to be performed during the MDV3 project will refine the hardware detailed requirements, document a hardware development plan, prepare the hardware design, develop the system test plan and test procedures to be used for validation, and build the production lines of hardware equipment to produce the Magical Devices Version 3.

The hardware deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 6 - Hardware Work

As the system architecture and the hardware design are finalized, the “Hardware Procurement” deliverable will be refined into greater detail to break out the individual elements of equipment required for staging, piece build, assembly, finishing, QA, management stations, control stations, and magic dust.

Software

The software work to be performed during the MDV3 project will refine the software detailed requirements, document a software development plan, prepare the software design, develop the software test plan and test procedures to be used for validation, and build the software to produce the Magical Devices Version 3.

The software deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 7 - Software Work

As the system architecture and the software design are finalized, the “Software Procurement” deliverable will be refined into greater detail to break out the individual elements of procured software required for the production equipment, management stations, and control stations.

Security

The security work to be performed during the MDV3 project will refine the security detailed requirements, develop the security architecture, and develop the security test plan and test procedures to be used for validation and certification of the secure system.

The security deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 8 - Security Work

Facility

The facility work to be performed during the MDV3 project will refine the facility detailed requirements, document a facility build plan, prepare the facility design, and build the internal elements of the facility to produce the Magical Devices Version 3.  The external elements of the building itself will be constructed by the building contractor selected during the design process.

The facility deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.  As the facilities design is completed, the “Facilities Procurement” deliverable will be refined to break out the individual elements of building material required to complete the facilities build.

Figure 9 - Facility Work

Quality Assurance

The quality assurance work to be performed during the MDV3 project will ensure the hardware, software, system, security, and facility are fully tested and inspected to meet all the requirements, are correctly configured, and will be of the highest quality and fit for purpose to produce the Magical Devices Version 3.

The quality assurance deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 10 - Quality Assurance Work

Implementation

The implementation work to be performed during the MDV3 project will prepare and manage a comprehensive implementation plan to ensure the success of a multi-phase pilot and rollout of the production system to produce the Magical Devices Version 3.

The implementation deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 11 - Implementation Work

Training

The training work to be performed during the MDV3 project will refine the training detailed requirements, develop a training plan, prepare the material to train the users of the production system, and train the teams.

The training deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 12 - Training Work

Support

The support work to be performed during the MDV3 project will refine the support detailed requirements, develop a support plan, prepare the package of documentation and processes to support the system and facilities, and transition support to the operations teams.

The support deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 13 - Support Work

Project Management

The project management work to be performed during the MDV3 project will establish the project management office to manage the project as it progresses through execution and closing, hold a kick-off meeting to coordinate all members of the project, manage the risk budget, and conduct the activities required to successfully close out the project.

The project management deliverables are shown in the WBS extract shown below.  More information on each deliverable can be found in the WBS Dictionary in Appendix B.

Figure 14 - Project Management Work

Scope Verification

All work that is delivered into the final product shall undergo verification by both the project teams that produced the deliverables as well as independent verification by the Quality Assurance organization to ensure they are compliant with all requirements and are fit for purpose – able to fully meet the need for which they were intended.

Before each deliverable is completed, the project teams shall first conduct verification of their own work to ensure it is defect free and meets all the project requirements before they pass it on for Quality Assurance verification.  The deliverable owners will not rely on the QA process to find issues and defects.

Quality assurance shall then conduct formal verification to confirm the project outputs are correctly built and configured.  Any issues or deficiencies shall be documented and corrective actions then defined by the deliverable owner.  The corrections shall be implemented with all due speed by the deliverable owners, and then the work re-verified by quality assurance.  A deliverable shall not pass verification until the quality assurance organization formally confirms all issues have been addressed and the work is ready to passed on to the next step.

Verifications may be conducted through inspections, demonstrations, analyses, or tests as appropriate.  Verifications shall be conducted throughout the project as individual elements, drafts, versions, increments, or sprints are completed to find issues and enable correction well before the final deliverable is baselined.

Wherever possible, scenario based verification shall be used, where the verification event is conducted in the context of an example of actual use of the deliverable to obtain the most realistic verification it meets all the requirements and ensure it is clear that the work is fit for purpose at the same time.  The to-be business processes developed as part of the first steps of the project will be the basis for these scenarios wherever applicable.

Where appropriate, thresholds for issues and defects shall be established to allow minor issues to be corrected during the support phase while enabling the work to proceed to the next stage.  Where this approach is deemed appropriate, quality assurance shall work with the project team and customer groups to establish criteria according to the following structure:

- There must be zero Category 1 issues – affecting core functionality.

- There must be less than N (e.g. 3) Category 2 issues – where a workaround acceptable to the customer representative exists until the issue is corrected in a timely manner.

- There must be less than M (e.g. 5) Category 3 issues – minor usability not affecting use that the customer representative agrees can addressed during support or the next phase of the project.

Where the above thresholds are deemed useful for evaluation of deliverables they shall be agreed and documented during test planning before the deliverable testing commences.

Schedule

This section documents the MDV3 schedule baseline, mapping the project work defined in the work breakdown structure to the calendar in order to determine the project duration and the critical path driving the end-date.

The schedule logic is provided in Section 3.1 – Precedence Diagram.  The precedence diagram mapped to the calendar showing when work will be done and providing the overall project duration is provided in Section 3.2 – Gantt Schedule.  The critical path driving the project duration and end-date is provided in Section 3.3 – Critical Path.  The major project milestones are documented in Section 3.4 – Milestones.

The baseline schedule meets both of the schedule constraints specified in the initiation stage project charter:

| Charter Constraint | Planning Baseline |
| --- | --- |
| The total schedule must not exceed 36 months | The planned schedule is less than 32 months. |
| Pilot operation of the first production line must begin within 25 months from project start. | The first production pilot begin at the end of month 25. |

The above constraints have been included as milestones in the Gantt schedule shown in Section 3.4 - Milestones.

The current status of the schedule progress shall be reported each month to the Sponsor, Customer, and other relevant Stakeholders at the Monthly Project Review described in Section 9.2 – Monthly Project Review Meetings.  The schedule performance shall be reported using Earned Value Management.

Any changes to the project schedule once this plan is approved and baselined must go through the formal change control process described in Section 12 – Change Control Process.

Precedence Diagram

The MDV3 precedence diagram documents the execution logic of the project, flowcharting the deliverables to show the dependencies between them and the order in which the project work will be carried out.

The Project Manager and Leads conducted several iterations of planning to baseline a complete and accurate precedence diagram documenting the relationships between all of the project work.  The full MDV3 precedence diagram is shown in the diagram below, and can be zoomed in for greater visibility in this Project Management Plan document Microsoft Word soft-copy.  The full sized diagram can also be viewed or printed in full size A0 size paper from the attached documents “MDV3 Precedence Diagram” in PowerPoint, and “MDV3 Precedence Diagram - PDF” in PDF format.

Figure 15 - Precedence Diagram

This precedence diagram provides the logical structure of the project work that is then mapped to the calendar as shown in the Gantt Schedule in the following section.

Gantt Schedule

The Project Leads prepared detailed activity breakdowns for all of their deliverables to obtain duration estimates for all the elements of work.  The precedence diagram structure and these estimates were then loaded into Microsoft Project to obtain a Gantt schedule showing the mapping of the project work to the calendar, including calculation of the critical path driving the project end-date.  This Gantt schedule provides the formal MDV3 schedule baseline.

The following pages provide three views of the project Gantt schedule:

- Full Schedule.  This view shows the full Gantt schedule with the work listed in the order it was entered according to the structure of the Work Breakdown Structure, including the summary tasks identifying the functional areas by WBS header.  The critical path is highlighted in red.  You can also view or print this graphic in PDF format on full size A0 size paper in the attached file “MDV3 Gantt Schedule (Full) - PDF”.

- Summary Tasks.  This view shows the Gantt schedule summary tasks at the level of the WBS headers, showing the broad calendar ranges in which the work is being done.  You can also view or print this graphic in PDF format on full size A0 size paper in the attached file “MDV3 Gantt Schedule (Summary Tasks) - PDF”.

- Calendar Order.  This view shows the lowest level deliverables by themselves without the summary task WBS headers, listed in order of finish date, showing all the work of the project in the calendar order in which it is planned to be completed.  The critical path is highlighted in red.  You can also view or print this graphic in PDF format on full size A0 size paper in the attached file “MDV3 Gantt Schedule (Calendar Order) - PDF”.

These graphics can be zoomed in for greater visibility in this Project Management Plan document Microsoft Word soft-copy.  The full Gantt schedule including all of the resource allocations and other relevant information can also be found in the attached Microsoft Project file “MDV3 Gantt Schedule”.

Figure 16 - Gantt Schedule (Full)

Figure 17 - Gantt Schedule (Summary Tasks)

Figure 18 - Gantt Schedule (Calendar Order)

Critical Path

A subset of the MDV3 Gantt schedule showing just the deliverables on the project critical path is shown below, listed in order of finish date, showing the work driving the project duration and end-date in the calendar order in which it is planned to be completed.

Figure 19 – Gantt Schedule (Critical Path)

Performance of this work on schedule is essential to avoid any delays to the overall project and shall be a particular focus of the Project Manager and Project leads.  Resources shall be moved from non-critical path work to deliverables on the critical path wherever practical if the critical path work requires additional resources to maintain the schedule performance.

The figure above can be zoomed in for greater visibility in this Project Management Plan document Microsoft Word soft-copy.  You can also view or print this graphic in PDF format on full size A0 size paper in the attached file “MDV3 Gantt Schedule (Critical Path) - PDF”.

A listing of the work on the critical path can also be found in the table below, sorted into calendar order by start date, showing the work in the order it is planned to be completed.

| WBS-ID | Deliverable | Duration | Start | Finish |
| --- | --- | --- | --- | --- |
| PMA1.2 | Kick-off Meeting | 1 day | 2050-01-03 | 2050-01-03 |
| BPRT1.1 | Business Processes To-Be Draft | 20 days | 2050-01-04 | 2050-01-31 |
| BPRT1.2 | Business Processes To-Be Final | 10 days | 2050-02-01 | 2050-02-14 |
| GAN1.1 | Gap Analysis Draft | 20 days | 2050-02-15 | 2050-03-14 |
| GAN1.2 | Gap Analysis Final | 10 days | 2050-03-15 | 2050-03-28 |
| SYA1.1 | System Architecture Draft | 20 days | 2050-03-29 | 2050-04-25 |
| SYA1.2 | System Architecture Final | 10 days | 2050-04-26 | 2050-05-09 |
| SWP1.1 | Software Detailed Requirements | 20 days | 2050-05-10 | 2050-06-06 |
| SWP1.2 | Software Development Plan | 10 days | 2050-06-07 | 2050-06-20 |
| SWD1.1 | Software Design Draft 1 | 20 days | 2050-06-21 | 2050-07-18 |
| SWD1.2 | Software Design Draft 2 | 20 days | 2050-07-19 | 2050-08-15 |
| SWD1.3 | Software Design Final | 10 days | 2050-08-16 | 2050-08-29 |
| SWB1.1 | Software Procurement | 10 days | 2050-08-30 | 2050-09-12 |
| SWB1.2 | Software Sprint 1 | 30 days | 2050-09-13 | 2050-10-24 |
| QASW1.1 | Software Sprint 1 Test | 5 days | 2050-10-25 | 2050-10-31 |
| SWB1.3 | Software Sprint 2 | 30 days | 2050-11-01 | 2050-12-12 |
| QASW1.2 | Software Sprint 2 Test | 5 days | 2050-12-13 | 2050-12-19 |
| SWB1.4 | Software Sprint 3 | 30 days | 2050-12-20 | 2051-01-30 |
| QASW1.3 | Software Sprint 3 Test | 5 days | 2051-01-31 | 2051-02-06 |
| SWB1.5 | Software Sprint 4 | 30 days | 2051-02-07 | 2051-03-20 |
| QASW1.4 | Software Sprint 4 Test | 5 days | 2051-03-21 | 2051-03-27 |
| SWB1.6 | Software Sprint 5 | 30 days | 2051-03-28 | 2051-05-08 |
| QASW1.5 | Software Sprint 5 Test | 5 days | 2051-05-09 | 2051-05-15 |
| SWB1.7 | Software Final | 10 days | 2051-05-16 | 2051-05-29 |
| SYB1.1 | System Build 1 | 20 days | 2051-05-30 | 2051-06-26 |
| QASY1.1 | System Build 1 Test | 10 days | 2051-06-27 | 2051-07-10 |
| SYB1.2 | System Build 2 | 20 days | 2051-07-11 | 2051-08-07 |
| QASY1.2 | System Build 2 Test | 5 days | 2051-08-08 | 2051-08-14 |
| SYB1.3 | System Build Final | 10 days | 2051-08-15 | 2051-08-28 |
| QASC1.1 | Security Test | 10 days | 2051-08-29 | 2051-09-11 |
| QASE1.1 | Security Certification Final | 10 days | 2051-09-12 | 2051-09-25 |
| QASEC1.2 | System Certification Final | 10 days | 2051-09-26 | 2051-10-09 |
| SUPA1.4 | Support Package Final | 15 days | 2051-10-10 | 2051-10-30 |
| IMPP1.6 | Implementation Readiness Review | 5 days | 2051-10-31 | 2051-11-06 |
| PMRB1.1 | Risk Buffer | 51 days | 2051-11-07 | 2052-01-16 |
| TRPH1.1 | Phase 1 Training | 10 days | 2052-01-17 | 2052-01-30 |
| IMPH1.1 | Phase 1 Pilot | 20 days | 2052-01-31 | 2052-02-27 |
| IMPH2.1 | Phase 2 Pilot | 20 days | 2052-02-28 | 2052-03-26 |
| IMPH3.1 | Phase 3 Pilot | 20 days | 2052-03-27 | 2052-04-23 |
| IMPH3.2 | Phase 3 Rollout | 30 days | 2052-04-24 | 2052-06-04 |
| SUPS1.3 | Phase 3 Support Transition | 20 days | 2052-06-05 | 2052-07-02 |
| PMC1.1 | Project Closure Readiness Review | 1 day | 2052-07-03 | 2052-07-03 |
| PMC1.2 | Final Procurements Closure | 5 days | 2052-07-04 | 2052-07-10 |
| PMC1.3 | Lessons Learned Meeting | 1 day | 2052-07-11 | 2052-07-11 |
| PMC1.4 | Lessons Learned Report | 5 days | 2052-07-12 | 2052-07-18 |
| PMC1.5 | Project Final Report | 10 days | 2052-07-19 | 2052-08-01 |

Table 4 - Critical Path Deliverables

Milestones

The MDV3 project milestones mark events where important elements of work are completed that significantly move the project forward.  The status of progress towards the milestones will be presented at each Project Monthly Review, and will be a particular focus of management attention.

Two milestones were defined by the Sponsor in the Initiation Project Charter:

- Total schedule of less than 36 months.  The schedule achieves this, totalling less than 32 months in duration.

- Start of first pilot by end of month 25.  The schedule achieves this, starting the first pilot by the end of month 25, marked in the Gantt chart by the start of milestone “Implementation Phase 1”.

The rest of the project milestones were selected by the planning team to indicate the most significant points of achievement as the project progresses.

A Gantt schedule showing the project milestones as they fall across the calendar is shown in the following figure.  This graphic can be zoomed in for greater visibility in this Project Management Plan document Microsoft Word soft-copy.  You can also view or print this graphic in PDF format on full size A0 size paper in the attached file “MDV3 Gantt Schedule (Milestones) - PDF”.

Figure 20 - Gantt Schedule (Milestones)

A listing of the major project milestones and their end dates can also be found in the table below.

| WBS-ID | Deliverable | Finish |
| --- | --- | --- |
| SYA1 | System Architecture | Mon 50-05-09 |
| SECD1 | Security Design | Mon 50-06-13 |
| SWD1 | Software Design | Mon 50-08-29 |
| FACD1 | Facilities Design | Mon 50-10-10 |
| SECTP1 | Security Test Planning | Mon 50-10-31 |
| QAHW1 | Hardware Test | Mon 51-02-27 |
| HWB1 | Hardware Build | Mon 51-03-13 |
| QASW1 | Software Test | Mon 51-05-15 |
| SWB1 | Software Build | Mon 51-05-29 |
| QASY1 | System Test | Mon 51-08-14 |
| SYB1 | System Build | Mon 51-08-28 |
| FACI1 | Facilities Inspection | Mon 51-09-18 |
| QASE1 | Security Certification | Mon 51-09-25 |
| QASEC1 | System Certification | Mon 51-10-09 |
| FACB1 | Facilities Build | Mon 51-10-23 |
| SUPA1 | Support Package | Mon 51-10-30 |
| IMPH1 | Implementation Phase 1 | Tue 52-04-09 |
| IMPH2 | Implementation Phase 2 | Tue 52-05-07 |
| IMPH3 | Implementation Phase 3 | Tue 52-06-04 |
| SUPS1 | Phase Support | Tue 52-07-02 |
| PMC1 | Project Closure | Thu 52-08-01 |

Table 5 - Project Milestones

Budget

This section documents the baseline MDV3 budget, describing all the costs planned to be expended over the course of the project.

The total planned cost of the project is $44,467,360.  Additional information is provided in the following sections, including a breakdown of the cost per major deliverable, a summary of the resource costs by type, and a cost curve graphing the planned spending across time.

The baseline budget meets the financial constraint specified in the initiation project charter:

| Charter Constraint | Planning Baseline |
| --- | --- |
| The budget for this project must not exceed the business case estimate of $47,464,650. | The planned budget of $44,467,360 is approximately 6% less than the charter constraint. |

The current status of the budget progress shall be reported each month to the Sponsor, Customer, and other relevant Stakeholders at the Monthly Project Review described in Section 9.2 – Monthly Project Review Meetings.  The cost performance shall be reported using Earned Value Management metrics.

Any changes to the project budget once this plan is approved and baselined must go through the formal change control process described in Section 12 – Change Control Process.

Deliverable Costs

The Project Leads prepared a detailed activity breakdown for each of their deliverables including all resources, material, and services required to produce the deliverables in order to obtain complete cost estimates for all the elements of work.

A breakdown of the project cost at the deliverable summary level is provided in the table below.  Additional information on the costs of the lowest level deliverables can be found in the cost column of the Microsoft Project file “MDV3 Gantt Schedule” and “MDV3 Gantt Schedule (Full) - PDF”.  Cost accounts to be used for tracking all cost expenditure for each deliverable were assigned by the finance department, and can be found in the cost account column of the WBS Dictionary in Appendix B.

| WBS-ID | Deliverable | Cost |
| --- | --- | --- |
| MDV3 | Magical Devices V3 Project | $44,467,360 |
| BPR1 | Business Process | $324,000 |
| BPRA1 | Business Process As-IS | $26,400 |
| BPRT1 | Business Process To-Be | $105,600 |
| GAN1 | Gap Analysis | $132,000 |
| SYS1 | System | $978,000 |
| SYA1 | System Architecture | $105,600 |
| SYTP1 | System Test Planning | $140,800 |
| SYB1 | System Build | $361,600 |
| HW1 | Hardware | $11,143,100 |
| HWP1 | Hardware Planning | $105,600 |
| HWD1 | Hardware Design | $154,000 |
| HWTP1 | Hardware Test Planning | $96,800 |
| HWB1 | Hardware Build | $10,566,700 |
| SW1 | Software | $7,103,800 |
| SWP1 | Software Planning | $105,600 |
| SWD1 | Software Design | $352,000 |
| SWTP1 | Software Test Planning | $272,800 |
| SWB1 | Software Build | $6,098,400 |
| SEC1 | Security | $360,200 |
| SECD1 | Security Design | $103,200 |
| SECTP1 | Security Test Planning | $132,000 |
| FAC1 | Facility | $11,444,600 |
| FACP1 | Facilities Planning | $123,200 |
| FACD1 | Facilities Design | $316,800 |
| FACB1 | Facilities Build | $10,624,600 |
| QA1 | Quality Assurance | $758,000 |
| QAHW1 | Hardware Test | $105,600 |
| QASW1 | Software Test | $132,000 |
| QASY1 | System Test | $52,800 |
| QASC1 | Security Test | $51,200 |
| QASE1 | Security Certification | $25,600 |
| QASEC1 | System Certification | $17,600 |
| FACI1 | Facilities Inspection | $123,200 |
| IMP1 | Implementation | $2,591,400 |
| IMPP1 | Implementation Planning | $334,400 |
| IMPH1 | Implementation Phase 1 | $572,000 |
| IMPH2 | Implementation Phase 2 | $572,000 |
| IMPH3 | Implementation Phase 3 | $572,000 |
| TR1 | Training | $845,000 |
| TRP1 | Training Planning | $30,800 |
| TRM1 | Training Material | $264,000 |
| TRPH1 | Training Phases | $79,200 |
| SU1 | Support | $1,599,400 |
| SUP1 | Support Planning | $52,800 |
| SUPA1 | Support Package | $352,000 |
| SUPS1 | Phase Support | $633,600 |
| PM1 | Project Management | $7,319,860 |
| PMA1 | Project Management Activities | $2,249,860 |
| PMRB1 | Risk Budget | $5,050,000 |
| PMC1 | Project Closure | $20,000 |

Table 6 – Major Deliverable Costs

Resource Costs

A listing of the costs of the resources used by the MDV3 project is provided in the table below, including summaries of the cost by major resource type.  The rate for personnel resources is the full loaded mid-point for each labour classification, including all indirect and overhead costs.

| Name | Work | Standard Rate | Cost |
| --- | --- | --- | --- |
| Group: 1.1-Material-Facility |  |  | $9,250,000 |
| Facility Build Contract | 1 Contract | $9,250,000 | $9,250,000 |
| Group: 1.2-Material-Building |  |  | $565,000 |
| Building Material Other | 1 Various | $100,000 | $100,000 |
| Building Material Production | 3 Line | $100,000 | $300,000 |
| Building Material Shipping | 1 Each | $40,000 | $40,000 |
| Building Material Staging | 1 Each | $50,000 | $50,000 |
| Building Material Stations | 1 Each | $75,000 | $75,000 |
| Group: 1.3-Material-Hardware |  |  | $9,700,000 |
| Control Station HW | 3 Each | $200,000 | $600,000 |
| Equipment-Assembly | 3 Each | $600,000 | $1,800,000 |
| Equipment-Finishing | 3 Each | $600,000 | $1,800,000 |
| Equipment-Piece Build | 3 Each | $600,000 | $1,800,000 |
| Equipment-QA | 3 Each | $600,000 | $1,800,000 |
| Equipment-Staging | 3 Each | $600,000 | $1,800,000 |
| Management Station HW | 1 Each | $100,000 | $100,000 |
| Group: 1.4-Material-Software |  |  | $4,400,000 |
| Control Station SW | 3 Each | $300,000 | $900,000 |
| Management Station SW | 1 Each | $200,000 | $200,000 |
| Production Software | 3 Line | $1,100,000 | $3,300,000 |
| Group: 1.5-Material-Magic Dust |  |  | $777,000 |
| Magic Dust | 1,000 gram | $777 | $777,000 |
| Group: 2.1-Project Leads | 26,264 hrs |  | $3,283,000 |
| Andre Young | 1,784 hrs | $125/hr | $223,000 |
| Byomkesh Bakshi | 2,224 hrs | $125/hr | $278,000 |
| Cathy Kerr | 1,024 hrs | $125/hr | $128,000 |
| Heidi Geis | 4,352 hrs | $125/hr | $544,000 |
| Henry Kiku | 4,512 hrs | $125/hr | $564,000 |
| Irwin Fletcher | 3,064 hrs | $125/hr | $383,000 |
| Jean Cunliffe | 3,792 hrs | $125/hr | $474,000 |
| Kong Qiu | 504 hrs | $125/hr | $63,000 |
| Mary Sperling | 2,984 hrs | $125/hr | $373,000 |
| Son Goku | 2,024 hrs | $125/hr | $253,000 |
| Group: 2.2-Project Team | 88,000 hrs |  | $9,680,000 |
| Business-Process-Team | 2,400 hrs | $110/hr | $264,000 |
| Facilities-Team | 11,360 hrs | $110/hr | $1,249,600 |
| Hardware-Team | 9,000 hrs | $110/hr | $990,000 |
| Implementation-Team | 18,640 hrs | $110/hr | $2,050,400 |
| QA-Team | 4,400 hrs | $110/hr | $484,000 |
| Security-Team | 1,840 hrs | $110/hr | $202,400 |
| Software-Team | 22,080 hrs | $110/hr | $2,428,800 |
| Support-Team | 9,440 hrs | $110/hr | $1,038,400 |
| System-Team | 5,440 hrs | $110/hr | $598,400 |
| Training-Team | 3,400 hrs | $110/hr | $374,000 |
| Group: 2.3-Consultant | 332 hrs |  | $66,400 |
| Security Certification Consultant | 332 hrs | $200/hr | $66,400 |
| Group: 3.1-Project Management | 13,460 hrs |  | $1,695,960 |
| Ellie Arroway | 5,384 hrs | $110/hr | $592,240 |
| Charles Wallace | 5,384 hrs | $150/hr | $807,600 |
| Jonathan Livingston | 2,692 hrs | $110/hr | $296,120 |
| Group: 3.2-Risk Budget |  |  | $5,050,000 |
| Risk Budget |  |  | $5,050,000 |

Table 7 – Resource Costs By Type

Cost Curve

A time-phased summary of the planned project budget expenditure across the calendar is provided below.

Figure 21 - Cumulative Cost Curve

The large jumps starting in 2050 September are caused by the initiation of procurement of the hardware, software, and facility build.  When these contracts are finalized during project execution, it is expected that the hardware and facility procurements will be negotiated with the suppliers to include time phased milestone payment plans based on progress of delivery, and so will end up spreading these expenditures more evenly across time.

Risks

This section describes the MDV3 risk management process, and provides a copy of the baseline risk register.  The total planned risk budget is 50.5 days and $5,050,000, and has been included in the baseline project budget and schedule.

Risk Management Process

The risk register and associated risk budget was prepared by the Project Manager and Project leads and refined in an iterative process through project planning.  Risks were identified by consideration of all the risks on our standard Risk Checklist, reference to the risk planning and lessons learned of the build of the Magical Devices Version 2 facility, and consultation with the project team.  Risks were quantified, response plans prepared to avoid or mitigate the risks to the greatest extent possible, backup plans prepared to deal with the event the risk occurred anyway, and a final quantified risk budget baselined.

The probability and time estimates for the risks were developed by the project team considering previous experience and using Delphi estimation.  The dollar estimates were developed with a cost impact analysis as a function of the estimated delay time and considering any other relevant costs, with delays calculated at $100K a day to including consideration of profit loss if the start of production is delayed.

The MDV3 Project Manager has accountability for management of the risk budget and successful performance of the project.  Ownership of individual risks has been allocated to the level closest and best able to manage the risk.  The risk register shall be reviewed at the end of each weekly status meeting.  The risk triggers shall be monitored by the risk owners, and action taken proactively to avoid or mitigate the risks everywhere possible.  Risk response plans shall be refined and improved throughout the project as required.  Funds shall be withdrawn from the risk budget to fund proactive measures to provide the greatest possible risk avoidance or mitigation at the earliest possible point possible.  If it becomes apparent a risk cannot be avoided, the backup plans shall be activated.

The Project Manager is the authorized signing authority for drawdown on the risk dollar budget.  To obtain funds from the budget the Project Manager shall submit a completed Risk Budget Drawdown Justification form (RBDJ-14e) to the MDV3 financial controller, fully documenting the status of the planned risk for which the funds are being accessed, or the reason they are needed for an unforeseen risk, the alternatives to drawdown of the risk budget that were considered and deemed unsuitable, and the justification for the amount being withdrawn.  Amounts requested in excess of 10% of the original risk budget baseline shall also require authorization by the Magical Devices VP Finance.

The risk time buffer has been scheduled according to the principles of critical chain management, in a single consolidated buffer before the critical customer event whose planned date should be most protected, which was determined to be directly before the start of the pilot rollout of the first production line.

The current status of the risk budget shall be reported each month to the Sponsor, Customer, and other relevant Stakeholders at the Monthly Project Review described in Section 9.2 – Monthly Project Review Meetings.

Any increases to the risk budget once this plan is approved and baselined must go through the formal change control process described in Section 12 – Change Control Process.

Risk Register

The MDV3 project risk register showing the known project risks, estimated schedule and cost impacts, owner, trigger, response plans, and backup plan can be found in the following pages.  The total planned risk budget of 50.5 days and $5,050,000 is provided in the last row of the risk register, summing up the amounts estimated to be required for all of the individual risks.

The full risk register can also be found in the attached document “MDV3 Risk Register”.  The full risk register also provides additional information on the quantification assessment before the risk response planning was applied.

| Risk | Risk Statement | P% | T (d) | $K | P x T | P x $K | Owner | Trigger | Response Plan | Backup Plan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Software Development Issues | If the software development effort is not accurately planned, estimated, and sufficiently staffed, the software development schedule will extend, increasing the project schedule and budget. | 30% | 30 | $3,000 | 9 | $900 | Byomkesh Bakshi, Software Lead | Status burndown charts of early sprints indicate the planned schedule is not achievable. | • The software development team incorporated all the lessons of the Magical Devices Version 2 project to prepare realistic estimates and plans for Version 3. • The version 3 software is building on the near feature complete prototypes developed by the R&D projects over the couple years. • Detailed software requirements are documented and development planning is conducted before design begins. • Several iterations of design are conducted before build commences. • Five sprints are planned, each incorporating testing and documentation, in addition to separate QA test cycles. | • Increase the software development team by dedicating the research and development personnel to the project until complete. • Review the software scope to see if there is any non-essential second priority scope that can be removed from the project or implemented in a later follow-on project. |
| Magic Dust Availability | If there is not sufficient magic dust available to complete integration of the equipment, the hardware builds will not be able to proceed, increasing the project schedule and budget. | 20% | 40 | $4,000 | 8 | $800 | Andre Young, Hardware Lead | Suppliers cannot commit to delivery dates when ordering. | • An advance order for 70% of the amount of magic dust anticipated to be required shall be made with our standard suppliers on the first day of execution of the project. • The remainder shall be ordered as the first step in hardware procurement. • An additional 15% was added to the planned costs to enable payment to suppliers for expedited delivery should it be needed. | Three backup suppliers have been identified, and sufficient research done to preliminarily qualify them as potential candidates should our regular suppliers be unable to fulfill our orders for any reason. |
| Manufacturing Integration Incompatibilities | If the interfaces between the new set of complex and innovative equipment are not completely compatible, there will be additional integration work required, increasing the project schedule and budget. | 30% | 25 | $2,500 | 7.5 | $750 | Mary Sperling, System Lead | The first build focusing on integration testing surfaces issues. | • Use only industry standard and proven interfaces. • The first hardware build will test interfaces for early validation. | • Add a dedicated interface resolution team to work in parallel to mainline project work to resolve issues as fast as possible. |
| Team Turnover | If team members do not find the project and organization sufficiently rewarding and enjoyable, they might leave for other opportunities, increasing the project schedule and budget. | 20% | 30 | $3,000 | 6 | $600 | Charles Wallace, Project Manager | Dissatisfaction is expressed to team leads or HR. | • Empower the team and reward initiative. • Provide competitive salary and benefits. • Provide sincere recognition and appreciation of effort. • Continue regular team-building including monthly lunches and quarterly off-site events. | • Human resources department to pro-actively establish channels to sources of qualified personnel, prepared to recruit new staff on very short notice with very attractive hiring packages. |
| Scope Changes | If the cost and schedule driving scope is not completely identified before project execution begins, it will be discovered once design and build are underway requiring significant replanning, increasing the project schedule and budget. | 20% | 25 | $2,500 | 5 | $500 | Kong Qui, Business Process Lead | Design reviews of prototypes, mockups, and walkthroughs identify missing or incorrect scope. | • Professional business analysts were used to identify all cost and schedule driving project requirements during planning. • Business process gap analysis is one of the early activities in the schedule. • Detailed requirements documents will be prepared and reviewed before each phase of design commences. • All design and build proceeds in several agile iterations to identify any problems and enable response at the earliest possible point. | • Perform a scope analysis to see if there is any non-essential second priority scope that can be removed from the project, or implemented in a later follow-on project, to avoid increasing this project's schedule and budget and delaying facility opening. |
| Security Certification Issues | If the manufacturing system does not meet all requirements of the Magical Management Institute standard Secure Device Manufacturing & Operations (MMI-321123-G), the security certification will be delayed, preventing opening of the facility, startup of production, and delaying availability of the devices on the market. | 20% | 20 | $2,000 | 4 | $400 | Cathy Kerr, Security Lead | Dry-run security testing during the system build testing surfaces issues. | • Dry-run testing of the security test procedures is incorporated as part of the system build testing to obtain early warning and resolution. • The leading consulting company Magical Security Certification Assurance Inc. will be retained to analyze the design and review the early builds to identify any issues and ensure proactive resolution. • Pilot production periods are built into all phase rollouts to enable any unexpected issues to be addressed before full production. | • Identify former directors, board members, and senior consultants from the Magical Management Institute and retain them analyze any issues and oversee the resolutions. |
| Procurement Delays | If the hardware equipment does not arrive on the expected schedule, the builds will not be able to proceed, increasing the project schedule and budget. | 20% | 20 | $2,000 | 4 | $400 | Andre Young, Hardware Lead | Shipment and delivery tracking indicate delays. | • Early notification of all hardware procurement requirements will be provided as the design phases progress, so the procurement department can proactively identify suppliers that can provide the items quickly once procurement commences. | • Turn to secondary suppliers and order required items with payments for expedited delivery. |
| Operational Surprises | If unexpected issues are revealed once the system is in actual operation, potentially difficult fixes and retrofits might be required delaying full production, increasing the project schedule and budget. | 20% | 20 | $2,000 | 4 | $400 | Son Goku, QA Lead | Inspection of devices from initial production runs identify issues. | • As per the Scope Change risk, a great emphasis has been placed on early scope identification and agile iterative design and builds to minimize surprises. • Each of the three production phases will first go through a low production run pilot. | • Establish a fully staffed and dedicated design, build, and operations team to provide rapid reaction remediation solutions. |
| Resource Unavailability | If personnel are not dedicated full-time to this project, they might be unavailable when required due to work on other projects, increasing the project schedule and budget. | 10% | 30 | $3,000 | 3 | $300 | Lucy Pevensie, President | Personnel indicate their work start time will be delayed due to other priorities. | • The President has indicated to all department heads that this project is the first priority for the organization, and personnel must be allocated full-time when required. | • Have President re-emphasize to the organization that this project is the first priority. |
| Total Risk Budget: |  |  |  |  | 50.5 | $5,050 |  |  |  |  |

Table 8 - Risk Register

Issues

The required resources, schedule, and budget to address all of the anticipated MDV3 project issues have been built into the baseline plan, with one issue outstanding.

The following issue lies outside the scope of this project to build the MDV3 facility, and is being managed by the Magical Devices executive team:

- The site adjacent to our current facility that was acquired for the new manufacturing facility was originally assumed to have sufficient electrical capacity to support full production.  The site capacity evaluation report (SCER) prepared during planning revealed a shortfall in electrical capacity of 25% from the anticipated need.  Therefore, as a separate project, Magical Devices VP Manufacturing Ezekiel Rawlins is working with the city of Oakville to ensure the power utility completes an upgrade to provide the expected requirement.  This work is planned for completion by the end of the third quarter following project start, and so should be ready more than a year in advance of being needed.  The MDV3 project shall track this issue, and raise it for Executive team action if delays threaten to impact the project’s projected production start date.  It is anticipated that the Magical Devices President may be able to leverage their existing relationship with the Mayor of Oakville to help manage this issue if required.

Stakeholders

This section describes the MDV3 key stakeholders.  The project stakeholders are affected and can affect the project, and therefore have been included in definition of the project scope and development of the project plan, and will be included in regular communications as the project progresses.  The key project stakeholders, along with their role, key need, priorities, and planned communications are described in the Stakeholder Register provided below.  This register can also be found in the attached document “MDV3 Stakeholder Register”.

| Name | Role | Key Need | Priorities | Communications |
| --- | --- | --- | --- | --- |
| Lucy Pevensie | Magical Devices President | Additional revenue generation. | Schedule, Cost, Scope | • Monthly project review update. |
| Ava Lee | Magical Devices VP Customer Satisfaction | Enhanced version 3 magical devices with at least 80 greater effectiveness. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for device design and development, coordination of device user reviews. |
| Solomon Gursky | Magical Devices VP Finance | Cost control. | Cost, Schedule, Scope | • Monthly project review update. • Immediate notification of any unexpected cost changes. |
| Ezekiel Rawlins | Magical Devices VP Manufacturing | The latest manufacturing processes and equipment. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for production line build and test, inspections, and user reviews. |
| Stephanie Plum | Magical Devices VP Human Resources | Timely notification of any changes in plans for staffing growth. | Schedule, Scope, Cost | • Monthly project review update. • Immediate notification of any changes in schedule. |
| Jack Reacher | Magical Devices VP Marketing & Sales | Knowledge of new device features and schedule availability. | Schedule, Scope, Cost | • Monthly project review update. • Immediate notification of any changes to scope. |
| Dave Robicheaux | Magical Devices Director of Facilities & Operations | Standards compliant and supportable facility. | Scope, Schedule, Cost | • Monthly project review update. • Involvement with project team for facility build and test, inspections, and user reviews. |
| Travis McGee | Mayor Oakville | Advance notice of hiring plans and schedule. | Schedule | • Monthly updates by phone or meeting from the President. • Immediate notification of any changes in hiring plans. • Invitation to facility opening. |
| Meg Murray | Executive Director Magical Management Institute (MMI) | Assurance of compliance with Magical Management Institute Regulations. | Scope | • Quarterly updates on project progress and regulatory compliance. • Invitation to facility opening. |

Table 9 - Stakeholder Register

Resources

This section describes the project team, provides a resource loading across time, and describes the plans for management of critical resources required to carry out the MDV3 project.

Project Team

The Project Team that will carry out the MDV3 project is shown in the following organization chart.

Figure 22 - Project Organization

Due to the critical importance of the MDV3 project to the company, the assigned Project Leads are the most senior and experienced members from each department.  The Project Leads report directly to the Project Manager for the purposes of carrying out the MDV3 project, and are responsible for management of all work and the team members in their functional area. The deliverables that each Project Lead is accountable for are listed in the owner column of the WBS Dictionary in Appendix B.

The various working level teams are drawn from the matrix, from the company functional departments.  To ensure there are no schedule delays, all team members shall be allocated full-time to this project during the periods they are required.

The roles and responsibilities of the MDV3 Project Sponsor, Project Manager, and Project Leads are described in the table below.

| Name | Role | Responsibilities |
| --- | --- | --- |
| Lucy Pevensie | Project Sponsor | • Approval of the project plan, scope, schedule, budget, and risk budget. • Approval to any changes to the plan baseline once the project is underway. • Chair of the monthly project reviews. • Maintenance of company support. • Resolution of any issues the Project Manager is unable to resolve. |
| Charles Wallace | Project Manager | • Preparation of a complete, accurate, and realistic project plan. • Management of the project to obtain the best scope, schedule, budget, and risk performance possible. • Management of the Project Leads. • Ensure the project result is fit for purpose and fully meets the stakeholder expectations. • Formal statusing of the project progress once a month. • Conduct of the monthly project reviews and presentation of the project status to the Sponsor and key stakeholders. • Chair of the weekly issues status meeting. |
| Ellie Arroway | Project Coordinator | • Provide administrative and other support to the Project Manager as needed. • Coordinate project meetings including the Monthly Review and Weekly Status meetings. • Maintain the project documentation including the Project Issues List and Risk Register, meeting minutes, and other documentation as required. |
| Jonathan Livingston | Project Scheduler | • Maintain the project Gantt schedule. • Obtain current progress status from the Project Leads and prepare the schedule status for the Monthly Project Reviews. • Prepare the Earned Value Reports for monthly reporting. |
| Kong Qiu | Business Process Lead | • Develop the as-is and to-be business process baselines, and perform a gap analysis to determine what work is needed to implement the to-be processes. • Manage the business process team and all associated work. |
| Mary Sperling | System Lead | • Develop the top-level system architecture, the system test plan and system test procedures, and build the integrated hardware and software system. • Manage the system team and all associated work. |
| Byomkesh Bakshi | Software Lead | • Refine the software detailed requirements, document a software development plan, prepare the software design, develop the software test plan and test procedures to be used for validation, and build the software to produce the Magical Devices Version 3. • Manage the software team and all associated work. |
| Andre Young | Hardware Lead | • Refine the hardware detailed requirements, document a hardware development plan, prepare the hardware design, develop the hardware test plan and test procedures to be used for validation, and build the hardware to produce the Magical Devices Version 3. • Manage the hardware team and all associated work. |
| Cathy Kerr | Security Lead | • Refine the security detailed requirements, develop the security architecture, and develop the security test plan and test procedures to be used for validation and certification of the secure system. • Manage the security team and all associated work. |
| Irwin Fletcher | Facilities Lead | • Refine the facility detailed requirements, document a facility build plan, prepare the facility design, put in place the procurement with the contractor building the external elements of the facility, and build the internal elements of the facility to produce the Magical Devices Version 3. • Manage the facilities team and all associated work. |
| Son Goku | Quality Assurance Lead | • Ensure the hardware, software, system, security, and facility are fully tested and inspected to meet all the requirements, are correctly configured, and will be fit for purpose to produce the Magical Devices Version 3. • Manage the quality assurance team and all associated work. |
| Heidi Geis | Implementation Lead | • Prepare and manage a comprehensive implementation plan to ensure the success of a multi-phase pilot and rollout of the production system to produce the Magical Devices Version 3. • Manage the implementation team and all associated work. |
| Jean Cunliffe | Training Lead | • Refine the training detailed requirements, document a training plan, prepare the material to train the users of the production system, and train the teams. • Manage the training team and all associated work. |
| Henry Kiku | Support Lead | • Refine the support detailed requirements, document a support plan, prepare the package of documentation and processes to support the system and facilities, and transition support to the operations teams. • Manage the support team and all associated work. |

Table 10 - Project Roles & Responsibilities

Resource Loading

The following graph shows the resource loading by number of hours for the labour category consisting of the Project Management Office, Project Leads, Project Teams, and Security Consultant, by quarter across the course of the project.

Figure 23 - Resource Loading

Individual resource loading graphs for individuals and specific functional teams may be obtained from the Resource Graphs in the attached Microsoft Project file “MDV3 Gantt Schedule”.

Critical Resources

Two resources have been deemed critical to the success of the MDV3 project: software engineers with expertise developing magical functionality, and magic dust.  The following sections describe the approach to management of these critical resources.

Software Engineers

The software engineering skill-set required to develop magical functionality is currently in high demand and difficult to acquire.  The project is taking the following approach to ensure these critical resources are available as needed to complete the project on schedule.

The Magical Devices Human Resources department performed a qualifications and availability assessment over the past year.  Working with national HR consulting companies, they have benchmarked the company salary structure with the rest of the market, and made adjustments where needed to ensure salaries meet or exceed those available elsewhere in the industry.

The HR department has also identified sources for recruitment of qualified magical functionality software developers.  They are participating in job fairs at universities and magical institutes to ensure wide awareness of the job opportunities with our company, and to recruit a steady pipeline of qualified candidates year over year.  The recruitment advertising budget was also increased by 25%, and has refocused its mix to allocate more of the spending on the online marketplaces where magical software developers are most likely to be engaged.

As a result, the project currently has sufficient software development resources qualified in magical development to carry out the project.  An emphasis has been placed on realistic planning to ensure the project execution goes as smoothly as possible.  There will be a continued focus on staff retention programs at the company level, including development, training, and feedback mechanisms, to ensure all staff work in an enjoyable and fulfilling environment and continue to see Magical Devices as an employer of first choice.

Magic Dust

A sufficient supply of gold, platinum, and titanium magic dust is essential for completion of the equipment integration during the build of the production lines.  Increasing demand for magic dust over the past several years has tightened the available supply, increased the time from order to delivery, and significantly increased prices.  The project is taking the following approach to ensure this critical resource will be available in sufficient supply to carry out this project.

An advance order for 70% of the amount of magic dust that is anticipated to be required for the entire project shall be made with our standard suppliers on the first day of execution of the project, to ensure a sufficient supply is on hand well before it is needed during the hardware build.  The remainder of the supply required shall be ordered as the first step in hardware procurement once the full requirement is known, to ensure the full amount will be available well before it is required as the hardware build completes.

In addition, during project planning the budget for magic dust was increased to meet the most likely projected costs based on the rate of increase over the past twelve months.  Another 15% was then added to the planned costs to enable payment to the suppliers for expedited delivery should this measure be needed.

Finally, three backup suppliers overseas have been identified, and sufficient research done to preliminarily qualify them as potential candidates for provision of the magic dust requirement should our regular suppliers be unable to fulfill our orders for any reason.  These backup options will be actioned immediately on any indication of delays from our regular supply channels.

The risk to supply of this critical resource has been added to the project risk register, with $800K available in the risk budget to address any issues if they arise.  The Hardware Lead Andre Young shall manage this risk closely as the project progresses.

Communications

This section describes the planned formal communications as the MDV3 project is carried out.

Formal project communications shall consist of weekly issue status meetings, monthly project review meetings, change control board meetings, monthly communications to the company personnel, quarterly updates to the Mayor of Oakville, quarterly updates to the Director of the Magical Management Institute, and a press conference on facility opening.  The following sections provide additional information.

Weekly Issue Status Meetings

The purpose of the Weekly Issue Status Meeting is to provide a regular communication touchstone for the core team to discuss project-level issues and risks, coordinate steps for further action where required, and keep the momentum of the MDV3 project going.

The Project Manager shall chair the meeting.  Attendees shall include the Project Leads.  The meeting shall be held each week at 9:00 on Monday mornings.  Duration shall be a maximum of one hour.

The team leads shall review the risks on the Project Issues List for action, update, or closure as required.  New issues shall be recorded and potential resolutions discussed as time permits.  The Project Coordinator shall distribute the updated list to all Project Leads at the conclusion of the meeting.  A copy of the template used for the Project Issues List can be found in Appendix C.

At the end of each meeting the team shall also review the project Risk Register, make any updates required, and coordinate further action as needed.

Monthly Project Review Meetings

The purpose of the Monthly Project Review Meetings is to provide a regular opportunity for the Project Manager to provide a project status update to the Sponsor, Customer, and Stakeholders each month, and enable senior management to provide any required oversight and direction.

The Sponsor Lucy Pevensie, Magical Devices President, shall chair the meeting.  The Project Manager Charles Wallace shall conduct the meeting.  Attendees shall include:

- Ava Lee, VP Customer Satisfaction.

- Solomon Gursky, VP Finance.

- Ezekiel Rawlins, VP Manufacturing.

- Dave Robicheaux, Director of Facilities & Operations.

- Stephanie Plum, VP Human Resources.

- Jack Reacher, VP Marketing & Sales.

The meeting shall be scheduled for one hour, and held at 13:00 on the first Tuesday of each month in the Executive boardroom.

At the start of each month, the Project Manager, Project Coordinator, and Project Scheduler shall gather the current status of the project scope, schedule, cost, and risks for presentation at the monthly review.  A one page report format shall be used, a copy of which is provided in Appendix D.  The current copy of the risk register shall also be available.  Any other relevant information shall be provided as required and requested.

The monthly project status shall be provided using Earned Value Management metrics.  Green, yellow, red statusing will be provided for cost and schedule performance, where the thresholds for the Cost Performance Index (CPI) and the Schedule Performance Index (SPI) are:

- Green:  Above 0.95, project status is acceptable.

- Yellow.  From 0.90 to 0.95, needs corrective action.

- Red:  Below 0.90, requires urgent attention.

The Project Manager will present the project status to the Stakeholders at the monthly review.  The Project Manager shall bring options and recommendations for resolution of any significant issues and risks wherever possible.  Assistance and direction on priorities shall be requested where needed.  Plans for further action shall be coordinated where needed.

Change Control Board Meetings

The purpose of the Change Control Board Meetings is to review all changes to the scope, schedule, budget, or previously baselined and approved deliverables such as designs and documentation, to ensure all potential impacts are identified, that project manager or sponsor approval is obtained as required, and appropriate communication of any approved changes takes place with all affected parties.  More information on this process can be found in Section 12 – Change Control Process.

Monthly Company Updates

The purpose of the Monthly Company Updates is to keep the company personnel informed on the progress of the new facility build.

An email from the Project Manager shall be sent to all company personnel once a month with an update on the project progress and the expectations for the new facility opening and production start date.  The Project Manager shall also provide a verbal update at the quarterly all-hands.

Mayor Of Oakville Updates

The purpose of the Mayor Of Oakville Updates is to keep the Mayor Travis McGee updated on the facility build progress, the status and any changes in hiring plans, and provide an invitation to the facility opening.

The updates shall be provided by the Magical Devices President quarterly by telephone or breakfast or lunch meeting as appropriate.

Executive Director Magical Management Institute Updates

The purpose of the Director Magical Management Institute Updates is to provide updates on project progress and regulatory compliance to Meg Murray, Executive Director of the Magical Management Institute, to ensure smooth progress towards eventual MMI certification of the Magical Devices Version 3.

The updates shall be provided quarterly by phone call from the Project Manager.  The MMI Executive Director shall be provided an invitation to the facility opening.

Facility Opening Press Conference

The purpose of the Facility Opening Press Conference is to inform the general public and citizens of Oakville about the opening of the new facility, and to generate international press coverage about the start of production and general availability of the Magical Devices Version 3.

The Magical Devices VP Marketing & Sales Jack Reacher and MDV3 Project Manager shall organize the press conference.  The event shall including a walkthrough of the new facility, and a demonstration of the first run of Magical Devices Version 3.  Invited attendees shall include the Mayor of Oakville and city councillors, and local, provincial, national, and international press, onsite and through virtual attendance.

Quality

This section describes the approach to management of quality throughout the MDV3 project.

The quality of the project outputs is of paramount importance to the success of the effort, and will be a key focus of the management and project team throughout the conduct of the project.

The four quality principles driving this project are derived from the Magical Devices Quality Assurance Standard driving all quality efforts at Magical Devices, and are summarized below:

- Planning.  “Quality must be planned in, not inspected in”.  While all project work shall be subject to inspection and test on completion, quality shall be embedded in the work by the teams as it is being done.

- Benefits.  Quality parts and processes reduce overall cost and schedule, since they increase efficiency, reduce the amount of testing needed, reduce acceptance issues, reduce certification issues, and reduce unexpected problems once in operation.

- Continuous Improvement.  The team will gather lessons learned throughout the project to continuously build on incremental improvement as the work progresses.

- Fit For Purpose.  All project outputs must be “Fit for purpose”, able to genuinely do the job for which they are intended, fully satisfying the needs of the Customer.  This requirement will also be included in the formal Terms and Conditions of all vendor contracts.

All project team members shall use the best practices and standards of their profession in the conduct of their work.  In addition, peer reviews and user reviews are built into the deliverable work as key contributors to help maximize the quality of the output.  More information on the use of peer reviews and user reviews is provided in the following sections.

Peer Reviews

Peer reviews are one of the most effective processes to ensure deliverables are high quality outputs that are fully fit for purpose.

There are two types of peer reviews that will be used on this project: informal peer reviews that will be used for all project deliverables, and formal peer reviews that are required for health, safety, and legal sensitive deliverables.  More information is provided below.

Informal Peer Reviews.

Informal peer reviews do not have the administrative overhead of formal peer reviews, and so are easy to implement for any type of work.  The process for informal peer reviews is formally documented in the Magical Devices Quality Assurance standard, and summarized below:

- The owner of every deliverable work output that is passed on to others on the project shall ensure it has had a peer review before being finalized.

- For large items of work, multiple peer reviews shall be held through the process of creation of the deliverable so that a review will require no more than an hour by each reviewer.

- A peer review should include two or three peers to provide a comprehensive review from more than one viewpoint.

- Wherever possible, the owner of the deliverable shall hold a single consolidation meeting with all of the peer reviewers to gather a consolidated set of comments and allow for comments by peers on each other’s recommendations.

- The owner of the deliverable may ask follow up questions for clarification of a comment, however shall refrain from disputing the accuracy of a comment so that the consolidation meeting stays focused on gathering a complete set of the comments.  To ensure a focus on this essential attribute of informal peer reviews, the deliverable owner shall say “Thank you” following receipt of each comment.

- The owner of the deliverable may then incorporate the comment in a revision of the deliverable or discard any comment as they see fit in their professional judgement.

- No formal records are required for informal peer reviews, although the owner must retain a record of reviewer comments in their personal files until the project has been successfully delivered in case they are ever required for review.

Formal Peer Reviews

Formal peer reviews are required for all deliverables that have health, safety, or legal requirements to make certain any issues are resolved before finalization.  The process for formal peer reviews is formally documented in the Magical Devices Quality Assurance standard, and summarized below:

- The Quality Assurance organization shall ensure every deliverable work output with health, safety, or legal requirements has had a formal peer review before being finalized.  A QA representative shall manage each formal peer review process.

- For large items of work, multiple formal peer reviews shall be held through the process of creation of the deliverable so that each review will require a manageable amount of work by each reviewer.

- A formal peer review should include three to five peers to provide a comprehensive review from more than one viewpoint.  The reviewers should be selected from outside of the project team wherever possible to ensure a full and unbiased review.

- Quality assurance shall convene and chair a single consolidation meeting with all of the peer reviewers to gather a consolidated set of issues and allow for comments by peers on each others recommendations.  There is no set duration for a formal peer review consolidation meeting.  The QA representative shall record and manage the consolidated set of issues from comment through resolution.

- The owner of the deliverable may ask follow up questions of a reviewer for clarification of issues, and may offer additional information if they believe an issue is not accurate.  In the event of a disagreement by the deliverable owner or reviewers on the accuracy of an issue, the QA representative shall call for a vote among the reviewers, not including the deliverable owner, with the QA representative breaking any ties.  The votes of each member on any issues in dispute, whether or not passed by majority vote, shall be recorded in the issue log for later follow-up if required.  The QA representative may in their sole discretion record an issue for follow-up if they believe it justified even if not agreed by majority vote.

- Each issue agreed, passed by majority vote, or included at the discretion of the QA representative shall then be reviewed by the deliverable owner and appropriately addressed by revision of the deliverable or by provision of additional relevant information not available during the consolidation review meeting.  Each resolution shall be reviewed by the original reviewers for approval.  The QA representative will usually defer to the original reviewer’s decision on sufficiency of a resolution, however, if agreement cannot be reached, the QA representative may pass an issue as resolved if they deem it appropriate, provided this decision is approved by the Director of QA.

- Formal records of all peer reviews and resolution actions shall be retained in the Quality Assurance files for a period of at least five years following the end of the project.

User Reviews

User reviews are also included in the project plan as key contributors to help ensure the project result is fit for purpose.

Almost all the work on the project has been planned along agile principles, structured in a series of increments, drafts, versions, or sprints with opportunities for review, formal statusing of progress, and early adjustment as needed to ensure the project stays on track and delivers the results required as the increments progress.  This approach applies not just to the software work, but also to the business process, system, hardware, facilities, and other work.

User reviews are incorporated in the work of the deliverables themselves and in the Quality Assurance tests and inspections to present the work completed so far to the end-users to obtain their in-progress assessment and identification of any scope errors, omissions, or other issues, for adjustment as needed in the next increment.

The customer is represented on this project by the following stakeholders, who shall coordinate attendance by the respective user groups and help manage and participate in reviews as described below:

| User Group Lead | Lead Reviews | Participate in Reviews |
| --- | --- | --- |
| Ava Lee, Magical Devices VP Customer Satisfaction | Software and devices. | System. |
| Ezekiel Rawlins, Magical Devices VP Manufacturing | Business processes, system, production lines, equipment elements of the training and support programs. | Facility. |
| Dave Robicheaux, Magical Devices Director of Facilities | Facility, facility elements of the training and support programs. | Production lines. |

Table 11 - User Review Lead / Participation

The process for conduct of user reviews is formally documented in the Magical Devices Quality Assurance standard, and summarized below:

- As deliverable drafts, builds, versions, increments, or sprints are finalized, a user review will be held with the applicable user group.  The deliverable team will present the work in progress to the user group, using presentations, walkthroughs, demonstrations, prototypes, and mockups as appropriate.

- User comments shall be collected by the user group lead in a review table, such as the template found in Appendix E.

- Following collection of all of the comments, under the direction of the user group lead, the users shall fill in the column “User Priority” to prioritize their comments using the following categories:

1 = Essential to the project objective.

2 = Valuable comment, however recommended for implementation in the next
      project or phase.

3 = For later investigation, insufficient information currently available.

- In a separate meeting, under the direction of the deliverable owner with participation from the Project Team Lead and Project Manager as required, the project team will review the user priorities and fill in the column “Project Priority” according to the same priority scale, in order to contribute their view on the best prioritization of the comments given their understanding of the likely scope, schedule, and budget impacts.

- The project team shall provide the user review table back to the user group lead.  Additional communications required to baseline the user priorities and project priorities shall be held as required.  The table will then be provided to the Project Sponsor to finalize the Sponsor Decision column reflecting their decision on which items should assessed for potential inclusion in the project.

- The Priority 1 items identified by the Sponsor shall then be entered into the change control process to determine a full impact analysis of the proposed change.  The change shall be included in the project and work commenced only if the change control process concludes with a Sponsor decision to implement the comment with full knowledge of the time and cost impacts, and communication to all affected parties has taken place as needed.

- The project team and user groups shall implement each user review iteration as quickly as possible to minimize the impact of any required changes, with the goal of obtaining a finalized user review table for presentation to the Sponsor within four days of the conclusion of each review, and analysis of the change impact of any Sponsor indicated proposed changes being completed within eight days.

Procurement

This section describes the approach to procurement on the MDV3 project.  The project requires procurement of the following elements:

- Facility.  A large contract with a building supplier to build the external elements of the facility, other than the integration elements for the production lines and management and control stations being built by Magical Devices.

- Building Material.  The material required for the Magical Devices facility team to build the internal elements of the facility required to integrate the production lines and management and control stations.

- Hardware Equipment.  The hardware equipment required for staging, piece build, assembly, finishing, and QA for each of the three production lines.

- Magic Dust.  The magic dust required for integration of the hardware equipment.

- Management Station & Control Station Hardware.  The computers and control units for the management station and the three production line control stations.

- Management Station Software.  The software for operation of the management station.

- Control Station Software.  The software for operation of the three control stations.

The approach for procurement of each these elements is described in the following sections.

Facility

A 5000 square meter production facility built on the site acquired adjacent to the current factory is required to house the new production facility.  A candidate set of construction companies was identified during planning that is potentially capable of building the facility.  A Solicitation of Interest (SOI) was sent to the companies listing the top-level facility requirements and requesting a response on their ability to build a compliant facility.  A shortlist of the top three respondents was baselined.

During project execution, following preparation of the detailed facility requirements, a request for proposal (RFP) will be sent to this list of companies requesting bids.  Vendors that comply with all the mandatory requirements will then be evaluated using a best value calculation based on a scoring of the firm’s years of experience building similar facilities, the workmanship guarantees, and warranty provisions, and then the company with the best score / bid price ratio will be selected to build the facility.

Building Material

The building material required for the Magical Devices facility team to build the internal elements of the facility required to integrate the production lines and management and control stations are commodity products, and so shall be procured through our existing standing offers, or through a request for quote process based on a complete set of specifications, followed by placement of a contract with the supplier providing the best price, availability, and warranty provisions.

Hardware Equipment

A suite of hardware is required for build of the staging, piece build, assembly, finishing, and QA stages of each of the three production lines.  This equipment is available from more than one supplier.  A candidate set of vendors was identified during planning that is potentially capable of supplying the anticipated elements.  A Solicitation of Interest (SOI) was sent to the vendors listing the top-level hardware requirements and requesting a response on their ability to provide compliant components.  A shortlist of the top five respondents was baselined.

During project execution, following preparation of the system architecture and detailed hardware requirements, a request for proposal (RFP) will be sent to this list of vendors requesting bids.  Vendors that comply with all the mandatory requirements will then be evaluated using a best value calculation based on a scoring of the firm’s years of experience providing the required equipment, the availability guarantees, and warranty provisions, and then the vendor with the best score / bid price ratio will be selected to provide the equipment.

Magic Dust

The magic dust required for integration of the hardware equipment is a commodity product provided it meets the required quality specifications, however it has been identified as a critical resource essential for completion of the project that is in high demand and short supply, and so its procurement is being addressed with special processes.  More information on the procurement approach for magic dust is provided in Section 8.3.2 – Magic Dust.

Management Station & Control Station Hardware

The computers and control units for the management stations and three production line control stations are commodity products, and so shall be procured through our existing standing offers, or through a request for quote process based on a complete set of specifications followed by placement of a contract with the supplier providing the best price, availability, and warranty.

Management Station Software

A suite of software is required to provide control of the assembled production lines and integrated management of the entire production facility.  A range of vendors provide generalized management software capable of integrating a range of different vendor equipment based on open management standards.  A candidate set of vendors was identified during planning that is potentially capable of supplying the anticipated elements.  A Solicitation of Interest (SOI) was sent to the vendors listing the top-level software requirements and requesting a response on ability to provide compliant components.  A shortlist of the top four respondents was baselined.

During project execution, following preparation of the system architecture and detailed hardware and software requirements, a request for proposal (RFP) will be sent to this list of vendors requesting bids.  Vendors that comply with all the mandatory requirements will then be evaluated using a best value calculation based on a scoring of the firm’s years of experience providing the required software, the availability guarantees, and warranty provisions, and then the vendor with the best score / bid price ratio will be selected to provide the software.

Control Station Software

The control station software used to manage the production lines is generally proprietary and dependent on the selected hardware equipment, and so procurement of the control station software will be included as part of the process for the procurement of the hardware equipment.

Change Control Process

This section describes the process to be used to ensure all proposed changes to the MDV3 project are managed in a controlled manner that take into account all the effects of any potential change.

Once this project plan is approved by the Sponsor, any changes to scope, schedule, budget, or the risk budget must go through the formal change control process, as documented in the Magical Devices Change Control Procedure, and summarized in this section.

In addition, any change to any deliverable once it is baselined and approved during project execution, such as designs and documentation, must also go through the formal change control process to ensure that all impacts of the change are identified and all affected parties are included in the analysis and communications.

A summary of the change control process is provided below:

- First the change must be formally documented on a Change Request Form, a copy of which is provided for convenience in Appendix F.

- If the change is urgently required due to imminent impact on the project success or imminent affect on health, safety, security, or legal compliance, the Project Manager may authorize the change immediately and then follow up with a full impact analysis and communications with the Sponsor, Customer, and other relevant parties as soon as practically possible.

- Otherwise a Change Control Board (CCB) meeting shall then be convened to evaluate the change with wide membership of any possibly affected party, including a representative from all project core and support functions.  The primary purpose of this first meeting shall be solely to identify all the areas of potential impacts.  The Project Manager shall chair the meeting.

- An individual that is closest to the change shall then be appointed to follow up after the first meeting to complete an analysis and determine the full impact of the change to scope, schedule, budget, risks, procurements, and any other affected project element.  Options and alternatives to address the change shall be considered.  An updated requirements baseline, work breakdown structure, precedence diagram, estimates, Gantt schedule, and risk register shall be prepared for the change and any options as needed.

- The Change Control Board shall then be reconvened to consider the impacts of the change and select the best option if more than one resolution is possible.

- If the Change Control Board considers the change to be necessary or otherwise beneficial, and it does not affect the baselined project scope, schedule, budget, or risk budget approved by the Sponsor, the Project Manager may authorize the change.

- Otherwise if the change affects the baselined scope, schedule, budget, or risk budget approved by the Sponsor, a recommendation on the change shall then be made by the Change Control Board, as approved by the Project Manager, and submitted to the Sponsor for their consideration.  The change shall not be initiated unless and until formal approval by the Sponsor is provided in writing.

- When a scope change results in an increase to the baselined project schedule and budget, options shall always be considered for removal of offsetting scope to minimize the impacts, and these options presented to the Sponsor and Customer wherever appropriate.

- Once a decision on the change is made, the rationale for the decision and all relevant documentation will be stored in the Change Control Log files.  If the change is approved, all required project documentation shall be updated, and all relevant parties shall be informed in a timely manner.

Requirements

This appendix provides a listing of the MDV3 project requirements, including the unique identifier, type, owner of each requirement, and preliminary traceability to the deliverables and test cases that will satisfy them.

The deliverable traceability will be refined to a more detailed level as the system, software, hardware, and facility designs are developed during execution.  The test case allocations are currently at the procedure level, and will be refined to individual test cases as the test documentation is developed.

| ID | Type | Requirement | Owner | Deliverable | Test Case |
| --- | --- | --- | --- | --- | --- |
| 1000 | Functionality | The magical devices shall be compliant with all requirements in the industry standard "Magic Componentry Functionality Standard" (Version 10.52) from the Magical Management Institute. | Ava Lee | SYB1.3 | SYTP1.4 |
| 1100 | Functionality | The magical devices shall weigh less than 10 grams. | Ava Lee | HWD1.3 | QAHW1.3 |
| 1200 | Functionality | The magical devices shall be capable of suspension of time for at least ten hours in the local universal neighborhood. | Ava Lee | SWD1.3 | QASW1.5 |
| 1300 | Functionality | The magical devices shall be capable of teleportation over a distance of at least 100 meters. | Ava Lee | SWD1.3 | QASW1.5 |
| 1400 | Functionality | The magical devices shall be capable of projection of holographic sightscapes that are dynamic and indistinguishable from reality from any angle and in any lighting. | Ava Lee | SWD1.3 | QASW1.5 |
| 1500 | Functionality | The magical devices shall be automatically updatable over the Internet and by telekinesis. | Ava Lee | SWD1.3 | QASW1.5 |
| 1600 | Functionality | The magical devices shall be remotely callable and able to transport themselves to the users location from anywhere on the planet. | Ava Lee | SWD1.3 | QASW1.5 |
| 1700 | Functionality | The magical devices shall be configurable to disguise themselves as a normal looking computer, book, or kitten. | Ava Lee | SWD1.3 | QASW1.5 |
| 1800 | Functionality | The magical devices shall be able to cooperate with other devices in the same network over WIFI and telecommunications networks. | Ava Lee | SWD1.3 | QASW1.5 |
| 1900 | Functionality | The magical devices shall be capable of transmutation of any metal or noble gas. | Ava Lee | SWD1.3 | QASW1.5 |
| 2000 | Functionality | The magical devices shall be producible in any colour, including iridescent. | Ava Lee | SWD1.3 | QASW1.5 |
| 2100 | Facility | The manufacturing facility shall be compliant with all requirements of the Magical Management Institute standard "Magic Manufacturing Requirements And Specifications" (MMI-654321-D). | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 2200 | Facility | The facility shall fully comply with all requirements of the Magical Management Institute standard "Safe Production Of Devices With Magical Properties" (MMI-987654-E). | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 2300 | Facility | The facility shall include separate material staging and shipping lines for rapidly decongested material management. | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 2400 | Facility | The facility shall comply with all requirements of the standard Design Considerations for "Airborne Molecular Contamination Filtration Systems" (IEST-G-CC035.1). | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 2500 | Equipment | The production lines shall include equipment to provide staging, piece build, assembly, finishing, and QA functions. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 2600 | Equipment | The production equipment shall comply with all requirements of the standard "Vibration Monitoring" (ISO 10816). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 2700 | Equipment | The production equipment shall comply with all requirements of the standard "Acoustic Emissions" (ISO 22096). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 2800 | Equipment | The production equipment shall comply with all requirements of "Nanotechnologies Materials Specifications" (ISO 12805). | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 2900 | Equipment | All production equipment shall run on 220V grounded power. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 3000 | Equipment | All production equipment shall incorporate single function emergency shutdown features. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 3100 | Equipment | All production equipment shall use industry standard interfaces capable of connecting to equipment from any other vendor using the same standard interface. | Ezekiel Rawlins | HWD1.3 | QAHW1.3 |
| 3200 | Management Station | The facility shall include a management station capable of instrumentation reporting and control over all production lines. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 3300 | Management Station | The management station software shall provide longitudinal tracking of all production line performance over time, with reporting available on quantity, productivity, efficiency, and availability, and be available broken down by mode, phase, and device type. | Ezekiel Rawlins | SWD1.3 | QASW1.5 |
| 3400 | Management Station | The management station software shall provide single screen dynamic dashboards tracking the performance of each production line. | Ezekiel Rawlins | SWD1.3 | QASW1.5 |
| 3500 | Control Station | The facility shall include independent control stations for each of the three production lines each providing separate integration, control, and reporting functionality. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 3600 | Control Station | The control station software shall be able to control all equipment on a production line from the allocated production station. | Ezekiel Rawlins | SWD1.3 | QASW1.5 |
| 3700 | Control Station | The control station software for any production line shall be configurable to be able to simultaneously control any of the other production lines. | Ezekiel Rawlins | SWD1.3 | QASW1.5 |
| 3800 | Supportability | The computing and manufacturing equipment componentry shall all be off-the-shelf and available from multiple suppliers. | Dave Robicheaux | HWD1.3 | QAHW1.3 |
| 3900 | Supportability | All equipment vendors shall utilize a quality assurance system that complies with all requirements of "Quality Management System" (CLSI QMS13-A). | Dave Robicheaux | HWD1.3 | QAHW1.3 |
| 4000 | Supportability | All operating system and middleware shall be free open source software. | Dave Robicheaux | SWD1.3 | QASW1.5 |
| 4100 | Regulatory | The manufacturing system shall be compliant with all security requirements in the industry standard "Secure Magical Device Manufacturing" (MMI-321123-G) from the Magical Management Institute. | Ava Lee | FACD1.4 | QASE1.1 |
| 4200 | Regulatory | The devices shall be compliant with all requirements in the industry standard "Magic Componentry Functionality Standard (V10.52)" from the Magical Management Institute. | Ava Lee | SYB1.3 | SYTP1.4 |
| 4300 | Capacity | The facility shall be capable of producing 1M units in year 1 of operation. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 4400 | Capacity | The facility shall be capable of production growth of 40% a year for at least ten years. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 4500 | Capacity | The facility shall be capable of producing version 1 and version 2 magical devices and component parts to provide long-term customer support. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 4600 | Capacity | The facility's three production lines shall each be configurable to be able to produce health, education, and environment devices. | Ezekiel Rawlins | FACD1.4 | FACI1.7 |
| 4700 | Availability | A failure in any single component shall not bring down the production capacity by more than 10%. | Dave Robicheaux | HWD1.3 | QASY1.2 |
| 4800 | Availability | The manufacturing system shall have 99.999% uptime. | Ezekiel Rawlins | SYB1.3 | SYTP1.4 |
| 4900 | Availability | The production equipment shall be capable of 24/7/365 operation. | Dave Robicheaux | SYB1.3 | SYTP1.4 |
| 5000 | Availability | The production equipment shall be capable of component level swap and replace for repair of any faults. | Dave Robicheaux | HWD1.3 | QAHW1.3 |
| 5100 | Environmental | The facility shall create zero untreated waste. | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 5200 | Environmental | The facility shall use renewable energy for all power requirements. | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 5300 | Environmental | All packaging shall be fully recyclable. | Dave Robicheaux | SYB1.3 | SYTP1.4 |
| 5400 | Environmental | The facility shall comply with all requirements of "Environmental Management Systems" (ISO 14001). | Dave Robicheaux | FACD1.4 | FACI1.7 |
| 5500 | Security | The facility shall be secure from unauthorized access, with secure biometric authentication required for entry. | Dave Robicheaux | FACD1.4 | QASE1.1 |
| 5600 | Security | Logon for operation and control of all equipment and control and management stations shall be by secure biometric access. | Ezekiel Rawlins | SWD1.3 | QASW1.5 |
| 5700 | Training | The training solution shall provide hands-on skills training immediately before deployment of each phase. | Ezekiel Rawlins | TRM1.4 | TRM1.4 |
| 5800 | Training | The training solution shall include online self serve refreshment training resources. | Ezekiel Rawlins | TRM1.4 | TRM1.4 |
| 5900 | Marketing | The magical devices shall be orderable online and fully customizable to the customer's requirements. | Jack Reacher | SYB1.3 | SYTP1.4 |
| 6000 | Marketing | A device ordered online shall immediately enter the manufacturing queue, and be automatically shipped to the customer address when ready. | Jack Reacher | SWD1.3 | QASW1.5 |
| 6100 | Procurement | All equipment vendors shall be ISO 9001 certified. | Ezekiel Rawlins | FACB1.1 | FACB1.1 |
| 6200 | Procurement | The facility building contractor shall have experience building at least five manufacturing facilities of 5,000 square meters or larger within the last five years. | Dave Robicheaux | FACB1.1 | FACB1.1 |

Work Breakdown Structure Dictionary

This appendix provides a work breakdown structure dictionary with more information on the deliverables documented in Section 2.4 - Work Breakdown Structure, including a unique identifier, description, owner, and cost account.

| WBS ID | Work Breakdown Structure Deliverable | Description | Owner | Cost Account |
| --- | --- | --- | --- | --- |
| MDV3 | Magical Devices Version 3 | The entire MDV3 project. | Charles Wallace | CA1000 |
| BPR1 | Business Process | Develop baselines for the as-is business processes, the to-be business processes, and then perform a gap analysis to determine what work is needed to implement the to-be processes. | Kong Qiu | CA2000 |
| BPRA1 | Business Process As-Is | Collect and document the existing set of as-is business processes to provide a consolidated baseline. | Kong Qiu | CA3000 |
| BPRA1.1 | Business Processes As-Is Draft | Gather a consolidated, organized baseline of all the current business processes used to produce version 2 of the magical devices, conduct a review, and identify areas of remaining work. | Kong Qiu | CA4000 |
| BPRA1.2 | Business Processes As-Is Final | Finalize a final baseline of all the current business processes used to produce version 2 of the magical devices. | Kong Qiu | CA5000 |
| BPRT1 | Business Process To-Be | Develop the to-be business processes to reflect the way we wish the new facility to perform. | Kong Qiu | CA6000 |
| BPRT1.1 | Business Processes To-Be Draft | Prepare the new set of business processes to produce version 3 of the magical devices, conduct a review, and identify areas of remaining work. | Kong Qiu | CA7000 |
| BPRT1.2 | Business Processes To-Be Final | Finalize a final baseline of the new set of business processes to produce version 3 of the magical devices. | Kong Qiu | CA8000 |
| GAN1 | Gap Analysis | Perform a gap analysis to determine what work is needed to implement the to-be processes. | Kong Qiu | CA9000 |
| GAN1.1 | Gap Analysis Draft | Prepare an analysis of the changes between the as-is and to-be business processes, and the elements that will need to be created or modified to meet the to-be processes, conduct a review, and identify areas of remaining work. | Kong Qiu | CA10000 |
| GAN1.2 | Gap Analysis Final | Prepare a final analysis of the changes between the as-is and to-be business processes, and the elements that will need to be created or modified to meet the to-be processes. | Kong Qiu | CA11000 |
| SYS1 | System | Develop the top-level system architecture, the system test plan and system test procedures, and build the integrated hardware and software system that will produce the magical devices version 3. | Mary Sperling | CA12000 |
| SYA1 | System Architecture | Develop the top-level system architecture documenting the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3. | Mary Sperling | CA13000 |
| SYA1.1 | System Architecture Draft | Prepare a draft system architecture of the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA14000 |
| SYA1.2 | System Architecture Final | Prepare a final system architecture baseline of the hardware, software, interfaces, and functional components of the system required to produce the magical devices version 3. | Mary Sperling | CA15000 |
| SYTP1 | System Test Planning | Develop the system test plan and test procedures to be used to validate the working system. | Mary Sperling | CA16000 |
| SYTP1.1 | System Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the system. | Mary Sperling | CA17000 |
| SYTP1.2 | System Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the system and verify it meets the system requirements, conduct a review, and identify areas of remaining work. | Mary Sperling | CA18000 |
| SYTP1.3 | System Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the system and verify it meets the system requirements, conduct a review, and identify areas of remaining work. | Mary Sperling | CA19000 |
| SYTP1.4 | System Test Procedures Final | Prepare a final baseline of the procedures to be used to test the system and verify it meets the system requirements. | Mary Sperling | CA20000 |
| SYB1 | System Build | Build the integrated hardware and software system. | Mary Sperling | CA21000 |
| SYB1.1 | System Build 1 | Build the first version of the system to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA22000 |
| SYB1.2 | System Build 2 | Build the second version of the system to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Mary Sperling | CA23000 |
| SYB1.3 | System Build Final | Build the final version of the system to be used to produce the magical devices version 3. | Mary Sperling | CA24000 |
| HW1 | Hardware | Refine the hardware detailed requirements, document a hardware development plan, prepare the hardware design, develop the hardware test plan and test procedures to be used for validation, and build the production lines of hardware equipment to produce the magical devices version 3. | Andre Young | CA25000 |
| HWP1 | Hardware Planning | Develop the hardware detailed requirements and a hardware development plan. | Andre Young | CA26000 |
| HWP1.1 | Hardware Detailed Requirements | Prepare detailed hardware requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for hardware design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Andre Young | CA27000 |
| HWP1.2 | Hardware Development Plan | Prepare a hardware development plan documenting the processes, personnel, facilities, and schedule required to develop the hardware solution. | Andre Young | CA28000 |
| HWD1 | Hardware Design | Prepare the design for the hardware to produce the magical devices version 3. | Andre Young | CA29000 |
| HWD1.1 | Hardware Design Draft 1 | Prepare a first draft of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA30000 |
| HWD1.2 | Hardware Design Draft 2 | Prepare a second draft of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA31000 |
| HWD1.3 | Hardware Design Final | Prepare a final baseline of a hardware design to meet all the detailed hardware requirements and produce the magical devices version 3. | Andre Young | CA32000 |
| HWTP1 | Hardware Test Planning | Develop the hardware test plan and test procedures to be used to validate the working system. | Andre Young | CA33000 |
| HWTP1.1 | Hardware Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the hardware. | Andre Young | CA34000 |
| HWTP1.2 | Hardware Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements, conduct a review, and identify areas of remaining work. | Andre Young | CA35000 |
| HWTP1.3 | Hardware Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements, conduct a review, and identify areas of remaining work. | Andre Young | CA36000 |
| HWTP1.4 | Hardware Test Procedures Final | Prepare a final baseline of the procedures to be used to test the hardware and verify it meets the detailed hardware requirements. | Andre Young | CA37000 |
| HWB1 | Hardware Build | Procure the equipment, and build the hardware to produce the magical devices version 3. | Andre Young | CA38000 |
| HWB1.1 | Hardware Procurement | Finalize all remaining hardware procurement not already in-house due to early procurement as the design was developed. As the system architecture and the hardware design are finalized, this item will be refined into greater detail to break out the individual elements of equipment required for staging, piece build, assembly, finishing, QA, management stations, control stations, and magic dust. | Andre Young | CA39000 |
| HWB1.2 | Hardware Build 1 | Build the first version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA40000 |
| HWB1.3 | Hardware Build 2 | Build the second version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA41000 |
| HWB1.4 | Hardware Build 3 | Build the third version of the hardware to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Andre Young | CA42000 |
| HWB1.5 | Hardware Build Final | Baseline the final version of the hardware to be used to produce the magical devices version 3. | Andre Young | CA43000 |
| SW1 | Software | Refine the software detailed requirements, document a software development plan, prepare the software design, develop the software test plan and test procedures to be used for validation, and build the software to produce the magical devices version 3. | Byomkesh Bakshi | CA44000 |
| SWP1 | Software Planning | Develop the software detailed requirements and a software development plan. | Byomkesh Bakshi | CA45000 |
| SWP1.1 | Software Detailed Requirements | Prepare detailed software requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for software design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Byomkesh Bakshi | CA46000 |
| SWP1.2 | Software Development Plan | Prepare a software development plan documenting the processes, personnel, facilities, and schedule required to develop the software solution. | Byomkesh Bakshi | CA47000 |
| SWD1 | Software Design | Prepare the design for the software to produce the magical devices version 3. | Byomkesh Bakshi | CA48000 |
| SWD1.1 | Software Design Draft 1 | Prepare a first draft of the software design to meet all the detailed software requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA49000 |
| SWD1.2 | Software Design Draft 2 | Prepare a second draft of the software design to meet all the detailed software requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA50000 |
| SWD1.3 | Software Design Final | Prepare a final baseline of the software design to meet all the detailed software requirements and produce the magical devices version 3. | Byomkesh Bakshi | CA51000 |
| SWTP1 | Software Test Planning | Develop the software test plan and test procedures to be used to validate the working system. | Byomkesh Bakshi | CA52000 |
| SWTP1.1 | Software Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct testing of the software. | Byomkesh Bakshi | CA53000 |
| SWTP1.2 | Software Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the software and verify it meets the detailed software requirements, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA54000 |
| SWTP1.3 | Software Test Procedures Draft 2 | Prepare a second draft of the procedures to be used to test the software and verify it meets the detailed software requirements, conduct a review, and identify areas of remaining work. | Byomkesh Bakshi | CA55000 |
| SWTP1.4 | Software Test Procedures Final | Prepare a final baseline of the procedures to be used to test the software and verify it meets the detailed software requirements. | Byomkesh Bakshi | CA56000 |
| SWB1 | Software Build | Procure off-the-shelf software, and build the software to produce the magical devices version 3. | Byomkesh Bakshi | CA57000 |
| SWB1.1 | Software Procurement | Finalize all remaining software procurement for not already in-house due to early procurement as the design was developed. As the system architecture and the software design are finalized, this item will be refined to break out the individual elements of software required for the production equipment, management stations, and control stations. | Byomkesh Bakshi | CA58000 |
| SWB1.2 | Software Sprint 1 | Develop the first iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA59000 |
| SWB1.3 | Software Sprint 2 | Develop the second iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA60000 |
| SWB1.4 | Software Sprint 3 | Develop the third iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA61000 |
| SWB1.5 | Software Sprint 4 | Develop the fourth iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA62000 |
| SWB1.6 | Software Sprint 5 | Develop the fifth iteration of the software to produce the magical devices version 3. | Byomkesh Bakshi | CA63000 |
| SWB1.7 | Software Final | Baseline the final version of the software to be used to produce the magical devices version 3. | Byomkesh Bakshi | CA64000 |
| SEC1 | Security | Refine the security detailed requirements, develop the security architecture, and develop the security test plan and test procedures to be used for validation and certification of the secure system. | Cathy Kerr | CA65000 |
| SECD1 | Security Design | Refine the security detailed requirements and develop the security architecture to be used to secure the system. | Cathy Kerr | CA66000 |
| SECD1.1 | Security Detailed Requirements | Prepare detailed security requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for security design, build, and testing, conduct a review, address any issues, and prepare a final baseline. | Cathy Kerr | CA67000 |
| SECD1.2 | Security Architecture | Prepare a baseline security architecture of the hardware, software, processes, and functional components required to meet the detailed security requirements. | Cathy Kerr | CA68000 |
| SECTP1 | Security Test Planning | Develop the security test plan and test procedures to be used for validation and certification of the secure system. | Cathy Kerr | CA69000 |
| SECTP1.1 | Security Test Plan | Prepare a test plan identifying the processes, personal, facilities, equipment, and schedule required to conduct security testing of the system. | Cathy Kerr | CA70000 |
| SECTP1.2 | Security Test Procedures Draft 1 | Prepare a first draft of the procedures to be used to test the system and verify it meets the detailed security requirements, conduct a review, and identify areas of remaining work. | Cathy Kerr | CA71000 |
| SECTP1.3 | Security Test Procedures Final | Prepare a final baseline of the procedures to be used to test the system and verify it meets the detailed security requirements. | Cathy Kerr | CA72000 |
| FAC1 | Facility | Refine the facility detailed requirements, document a facility build plan, prepare the facility design, put in place the procurement with the contractor building the external elements of the facility, and build the internal elements of the facility to produce the magical devices version 3. | Irwin Fletcher | CA73000 |
| FACP1 | Facilities Planning | Develop the facility detailed requirements and a hardware development plan. | Irwin Fletcher | CA74000 |
| FACP1.1 | Facilities Detailed Requirements | Prepare detailed facility requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, identifying the detailed specifications required for the facility design, build, and inspection, conduct a review, address any issues, and prepare a final baseline. | Irwin Fletcher | CA75000 |
| FACP1.2 | Facilities Build Plan | Prepare a build plan documenting the processes, personnel, equipment, and schedule required to develop the production facility. | Irwin Fletcher | CA76000 |
| FACD1 | Facilities Design | Prepare the design for the facility to produce the magical devices version 3. | Irwin Fletcher | CA77000 |
| FACD1.1 | Facilities Design Draft 1 | Prepare a first draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA78000 |
| FACD1.2 | Facilities Design Draft 2 | Prepare a second draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA79000 |
| FACD1.3 | Facilities Design Draft 3 | Prepare a third draft of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA80000 |
| FACD1.4 | Facilities Design Final | Prepare a final baseline of a facilities design to meet all the detailed facilities requirements and produce the magical devices version 3. | Irwin Fletcher | CA81000 |
| FACB1 | Facilities Build | Put in place the procurement with the facilities contractor, and build the internal elements of the facility to produce the magical devices version 3. | Irwin Fletcher | CA82000 |
| FACB1.1 | Facilities Procurement | Finalize all remaining facilities procurement not already in-house due to early procurement as the design was developed, and put the contract in place with the contractor building the external elements of the facility. As the facilities design is completed, this item will be refined to break out the individual elements of building material required to complete the facilities build. | Irwin Fletcher | CA83000 |
| FACB1.2 | Facilities Build 1 | Build the first version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA84000 |
| FACB1.3 | Facilities Build 2 | Build the second version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA85000 |
| FACB1.4 | Facilities Build 3 | Build the third version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA86000 |
| FACB1.5 | Facilities Build 4 | Build the fourth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA87000 |
| FACB1.6 | Facilities Build 5 | Build the fifth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA88000 |
| FACB1.7 | Facilities Build 6 | Build the sixth version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA89000 |
| FACB1.8 | Facilities Build 7 | Build the seventh version of the facility to be used to produce the magical devices version 3, conduct a review, and identify areas of remaining work. | Irwin Fletcher | CA90000 |
| FACB1.9 | Facilities Build Final | Build the final version of the facility to be used to produce the magical devices version 3. | Irwin Fletcher | CA91000 |
| QA1 | Quality Assurance | Conduct the quality assurance to ensure the hardware, software, system, security, and facility are fully tested and inspected to meet all the requirements, are correctly configured, and will be of the highest quality and fit for purpose to produce the magical devices version 3. | Son Goku | CA92000 |
| QAHW1 | Hardware Test | Conduct testing of the hardware to verify all the requirements are met. | Son Goku | CA93000 |
| QAHW1.1 | Hardware Build 1 Test | Conduct testing of the first hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA94000 |
| QAHW1.2 | Hardware Build 2 Test | Conduct testing of the second hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA95000 |
| QAHW1.3 | Hardware Build 3 Test | Conduct testing of the third hardware build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final baseline. | Son Goku | CA96000 |
| QASW1 | Software Test | Conduct testing of the software to verify all the requirements are met. | Son Goku | CA97000 |
| QASW1.1 | Software Sprint 1 Test | Conduct testing of the first software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA98000 |
| QASW1.2 | Software Sprint 2 Test | Conduct testing of the second software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA99000 |
| QASW1.3 | Software Sprint 3 Test | Conduct testing of the third software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA100000 |
| QASW1.4 | Software Sprint 4 Test | Conduct testing of the fourth software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next sprint. | Son Goku | CA101000 |
| QASW1.5 | Software Sprint 5 Test | Conduct testing of the fifth software sprint to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final baseline. | Son Goku | CA102000 |
| QASY1 | System Test | Conduct testing of the system to verify all the requirements are met. | Son Goku | CA103000 |
| QASY1.1 | System Build 1 Test | Conduct testing of the first system build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA104000 |
| QASY1.2 | System Build 2 Test | Conduct testing of the second system build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final build. | Son Goku | CA105000 |
| QASC1 | System Certification | Conduct formal certification of the system to be ready to procure the magical devices version 3. | Son Goku | CA106000 |
| QASC1.1 | System Certification | Review all the prior system, hardware, software, and security testing, validate the readiness for system operation, conduct any final certification activities required, and formally certify the system ready for production of the magical devices version 3. | Son Goku | CA107000 |
| QASE1 | Security Test | Conduct formal security certification of the system to be ready to produce the magical devices version 3. | Son Goku | CA108000 |
| QASE1.1 | Security Test Final | Conduct testing of the system to verify all the security requirements are met, conduct remediation of any deficiencies, and retest any areas required. | Son Goku | CA109000 |
| QASEC1 | Security Certification | Conduct testing of the software to verify all the requirements are met. | Son Goku | CA110000 |
| QASEC1.2 | Security Certification Final | Review the security testing, validate the readiness for secure operation, conduct any final certification activities required, and formally certify the system as secure for production of the magical devices version 3. | Son Goku | CA111000 |
| FACI1 | Facilities Inspection | Conduct inspections of the facility to verify all the requirements and design are met. | Son Goku | CA112000 |
| FACI1.1 | Inspection Build 1 | Conduct an inspection of the first facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA113000 |
| FACI1.2 | Inspection Build 2 | Conduct an inspection of the second facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA114000 |
| FACI1.3 | Inspection Build 3 | Conduct an inspection of the third facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA115000 |
| FACI1.4 | Inspection Build 4 | Conduct an inspection of the fourth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA116000 |
| FACI1.5 | Inspection Build 5 | Conduct an inspection of the fifth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA117000 |
| FACI1.6 | Inspection Build 6 | Conduct an inspection of the sixth facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the next build. | Son Goku | CA118000 |
| FACI1.7 | Inspection Build 7 | Conduct an inspection of the seventh facilities build to verify all the allocated requirements are met, document any deficiencies, and identify areas requiring remediation in the final build. | Son Goku | CA119000 |
| IMP1 | Implementation | Prepare and manage a comprehensive implementation plan to ensure the success of a multi-phase pilot and rollout of the production system to produce the magical devices version 3. | Heidi Geis | CA120000 |
| IMPP1 | Implementation Planning | Prepare an implementation plan documenting the processes, personnel, facilities, and schedule required to implement the production system. | Heidi Geis | CA121000 |
| IMPP1.1 | Implementation Plan Draft 1 | Prepare a first draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA122000 |
| IMPP1.2 | Implementation Plan Draft 2 | Prepare a second draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA123000 |
| IMPP1.3 | Implementation Plan Draft 3 | Prepare a third draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA124000 |
| IMPP1.4 | Implementation Plan Draft 4 | Prepare a fourth draft of the implementation plan for a three phase pilot and rollout of the production system, conduct a review, and identify areas to address in the next version. | Heidi Geis | CA125000 |
| IMPP1.5 | Implementation Plan Final | Prepare a final baseline of the implementation plan for a three phase pilot and rollout of the production system. | Heidi Geis | CA126000 |
| IMPP1.6 | Implementation Readiness Review | Review the system certification, security certification, facilities inspections, implementation plan, training material, and support package to determine readiness for progress to implementation. | Heidi Geis | CA127000 |
| IMPH1 | Implementation Phase 1 | Conduct a pilot and rollout of phase 1 of the system. | Heidi Geis | CA128000 |
| IMPH1.1 | Phase 1 Pilot | Pilot the first production line, ramping up to full capacity. | Heidi Geis | CA129000 |
| IMPH1.2 | Phase 1 Rollout | Rollout full capacity of the first production line. | Heidi Geis | CA130000 |
| IMPH2 | Implementation Phase 2 | Conduct a pilot and rollout of phase 2 of the system. | Heidi Geis | CA131000 |
| IMPH2.1 | Phase 2 Pilot | Pilot the second production line, ramping up to full capacity. | Heidi Geis | CA132000 |
| IMPH2.2 | Phase 2 Rollout | Rollout full capacity of the second production line. | Heidi Geis | CA133000 |
| IMPH3 | Implementation Phase 3 | Conduct a pilot and rollout of phase 3 of the system. | Heidi Geis | CA134000 |
| IMPH3.1 | Phase 3 Pilot | Pilot the third production line, ramping up to full capacity. | Heidi Geis | CA135000 |
| IMPH3.2 | Phase 3 Rollout | Rollout full capacity of the third production line. | Heidi Geis | CA136000 |
| TR1 | Training | Refine the training detailed requirements, develop a training plan, and prepare the material to train the users of the production system, and train the teams. | Jean Cunliffe | CA137000 |
| TRP1 | Training Planning | Refine the training detailed requirements and document a training plan to train the users of the production system. | Jean Cunliffe | CA138000 |
| TRP1.1 | Training Detailed Requirements | Prepare detailed training requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture. | Jean Cunliffe | CA139000 |
| TRP1.2 | Training Plan | Prepare a plan documenting the processes, personnel, facilities, and schedule required to develop the training solution. | Jean Cunliffe | CA140000 |
| TRM1 | Training Material | Prepare the material to train the users of the production system. | Jean Cunliffe | CA141000 |
| TRM1.1 | Training Material Draft 1 | Prepare the first draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA142000 |
| TRM1.2 | Training Material Draft 2 | Prepare the second draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA143000 |
| TRM1.3 | Training Material Draft 3 | Prepare the third draft of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA144000 |
| TRM1.4 | Training Material Final | Prepare the final baseline of the material to training the production team in use of the system to produce the magical devices version 3. | Jean Cunliffe | CA145000 |
| TRPH1 | Training Phases | Conduct three phases of training for the pilots and rollout of the production system. | Jean Cunliffe | CA146000 |
| TRPH1.1 | Phase 1 Training | Train the team in use of the first production line for producing the magical devices version 3. | Jean Cunliffe | CA147000 |
| TRPH1.2 | Phase 2 Training | Train the team in use of the second production line for producing the magical devices version 3. | Jean Cunliffe | CA148000 |
| TRPH1.3 | Phase 3 Training | Train the team in use of the third production line for producing the magical devices version 3. | Jean Cunliffe | CA149000 |
| SU1 | Support | Refine the support detailed requirements, develop a support plan, prepare the package of documentation and processes to support the system and facilities, and transition support to the operations teams. | Henry Kiku | CA150000 |
| SUP1 | Support Planning | Refine the support detailed requirements and document a support plan to support the system and facilities to produce the magical devices version 3. | Henry Kiku | CA151000 |
| SUP1.1 | Support Detailed Requirements | Prepare detailed support requirements based on the system requirements previously documented during the project planning stage, the gap analysis, and the system architecture, conduct a review, address any issues, and prepare a final baseline. | Henry Kiku | CA152000 |
| SUP1.2 | Support Plan | Prepare a support plan documenting the processes, personnel, facilities, and schedule required to develop the support solution. | Henry Kiku | CA153000 |
| SUPA1 | Support Package | Prepare the package of documentation and processes to support the system and facilities to produce the magical devices version 3. | Henry Kiku | CA154000 |
| SUPA1.1 | Support Package Draft 1 | Prepare the first version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA155000 |
| SUPA1.2 | Support Package Draft 2 | Prepare the second version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA156000 |
| SUPA1.3 | Support Package Draft 3 | Prepare the third version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA157000 |
| SUPA1.4 | Support Package Final | Prepare the final version of the package to be used to support the magical devices version 3 production system. | Henry Kiku | CA158000 |
| SUPS1 | Phase Support | Transition support to the operations teams. | Henry Kiku | CA159000 |
| SUPS1.1 | Phase 1 Support Transition | Transition support of the first production line from the development team to the operations support team. | Henry Kiku | CA160000 |
| SUPS1.2 | Phase 2 Support Transition | Transition support of the second production line from the development team to the operations support team. | Henry Kiku | CA161000 |
| SUPS1.3 | Phase 3 Support Transition | Transition support of the third production line from the development team to the operations support team. | Henry Kiku | CA162000 |
| PM1 | Project Management | Establish the project management office to manage the project as it progresses through execution and closing, hold a kick-off meeting to coordinate all members of the project, manage the risk budget, and conduct the activities required to successfully close out the project. | Charles Wallace | CA163000 |
| PMA1 | Project Management Activities | Establish the project management office to manage the project as it progresses, and hold a kick-off meeting to coordinate all members of the project. | Charles Wallace | CA164000 |
| PMA1.1 | Project Management Office | The project manager, project scheduler, and project coordinator for the entire project. | Charles Wallace | CA165000 |
| PMA1.2 | Kick-off Meeting | Assemble the full team to review the project plan, answer any questions, identify any unknown issues, conduct some team building, and set a coordinated foundation for the rest of the project. As per the risk management plan, 70% of the anticipated requirement for Magic Dust will also be procured on the first day of the project. | Charles Wallace | CA166000 |
| PMRB1 | Risk Budget | Manage the risk budget to minimize the risks to the project budget and schedule performance. | Charles Wallace | CA167000 |
| PMRB1.1 | Risk Buffer | Provide a risk buffer of time and cost to protect the pilot and rollout dates once the project plan is approved. | Charles Wallace | CA168000 |
| PMC1 | Project Closure | Conduct the activities required to close out the project. | Charles Wallace | CA169000 |
| PMC1.1 | Project Closure Readiness Review | Review the status of all previous elements of the project, and assure readiness for project closure. | Charles Wallace | CA170000 |
| PMC1.2 | Final Procurements Closure | Review the production line rollouts, support, and all remaining open procurements, resolve any outstanding issues, and conduct formal closure. | Charles Wallace | CA171000 |
| PMC1.3 | Lessons Learned Meeting | Review all lessons learned documentation collected during the project, conduct a final lessons learned all team meeting, and assemble a final set of lessons learned. | Charles Wallace | CA172000 |
| PMC1.4 | Lessons Learned Report | Prepare a final lessons learned report, send it to all stakeholders, and flow recommended actions to the relevant parts of the organizations. | Charles Wallace | CA173000 |
| PMC1.5 | Project Final Report | Prepare a project final report, documenting what happened with scope, time, cost, the business case, major risks, major lessons learned, and recommendations for next steps. | Charles Wallace | CA174000 |

Project Issues List Format

For convenient reference, this appendix provides a copy of the Project Issues List format used for the coordination of the Weekly Issues Status Meeting described in Section 9.1 – Weekly Issues Status Meetings.  The Project Issues list shall track the issue name, status, lead, and expected resolution due date for each issue.  This Microsoft Word table format is easily sortable with the Layout / Sort command after any additions or updates to put the issues in order by Lead / Due Date or Due Date / Lead as desired.

-----

Project ABC - Issues List

| Issue | Status | Lead | Due |
| --- | --- | --- | --- |
| Space Shortage | Converting meeting room 5 to working area with desks. | Anderson | 2050-01-15 |

Use:

* Add rows for new items as needed, and then collect together by Lead or Due Date with the menu item Table / Sort.

* Enter dates in format YYYY-MM-DD so the Layout / Sort command works consistently.

Monthly Project Report Format

This appendix provides the format of the one page report to be used for the monthly project review meetings in Section 9.2 – Monthly Project Review Meetings.

An example of the one page report can be found below.  The top left quadrant provides a Gantt schedule snapshot showing the current status of scope on schedule.  The top right quadrant provides status on the current cost performance, and for the MDV3 project shall include the current Earned Value metrics.  The bottom left quadrant provides the current status of the top three issues and risks.  And the bottom right quadrant provides any relevant information on the current status of the customer groups.

Additional information on project performance shall also be provided to the monthly review board as required and on request.  A copy of the current risk register will usually also be available for review.

User Review Template

For convenient reference, this appendix provides a copy of the review template used for the user review process summarized in Section 10.1.2 – Formal Peer Reviews.

-----

User Review: [Deliverable ABC Draft 1]

| Issue | User Priority | Project Team Priority | Sponsor Decision |
| --- | --- | --- | --- |
| Add this... | 1 | 1 | 1 |
| Change this... | 1 | 2 | 1 |
| Remove that... | 1 | 1 | 2 |
| Enhance that... | 1 | 1 | 1 |
| Add this... | 2 | 2 | 2 |
| Remove that... | 2 | 2 | 2 |
| Add that... | 2 | 2 | 3 |
| Change this... | 3 | 3 | 3 |
| Enhance that... | 3 | 3 | 3 |

Priorities:

1 = Essential to project objective, should be analyzed for impact if this is the final sponsor decision.

2 = Good idea, but recommended for next project or phase.

3 = Record for later investigation.

Change Request Form

For convenient reference, this appendix provides a copy of the formal Change Request form used for the process summarized in Section 12 - Change Control Process.

-----

Change Request

Instructions:  This form must be completed for any requested change to any baselined and approved project element, including scope, schedule, budget, risk budget, or project deliverables, no matter how minor, and submitted through the Project Manager for proper consideration of all the impacts and communications with all affected parties.

| Identification |  |
| --- | --- |
| Project: |  |
| Requester: |  |
| Date Of Request: |  |
| Requested Change |  |
| Change: |  |
| Reason / Benefit: |  |
| Known Impacts |  |
| Deliverables: |  |
| Requirements: |  |
| Contracts: |  |
| Schedule: |  |
| Cost: |  |
| Risks: |  |
| Other: |  |
| Alternatives & Options |  |
| Alternatives: |  |
| Options: |  |
| Sign Off |  |
| Requester: |  |
| Date: |  |

(Note: In a project of this size, it would not be unusual to include additional diagrams in this section, for example showing more top-level detail for the architecture of the production lines, management stations, and control stations, perhaps even a top-level software architecture.)